## SAMPLE
Project Meta Data
PROJECT TITLE: | Water supply pipe replacement | PMIS #: | 123456 | PEPC# 12345
PARK: | SEKI | REGION: PWR | PROGRAM: | DBB | Permit Lead: | Park
PARK CONTACT: | Nancy Hendrick | A\E: | Contractor X |  | DSC PM: R. Rampi
Dates of Assessment: 8/19/11 |  | A\E CONTACT: | NONE |  | DSC PS: D. Lindeman
Permits to Contracting no later than: 8/1/12
Notes: Project involves the replacement of a water pipeline including upgrading the water intake weir in a perennial creek. Wetland delineation is expected to be approved in February 2012.
Permits Required
PERMIT: CWA Section 404 Nation Wide Permit 12
Permit Standard: Sac. District NWP conditions |  | Date of information: 1/30/2012 |  | Consultation Started: July 2011
Issuing Agency: USACE Sacramento District |  | Application Fee: | No | Amount of Fee: $0.00
Agency Contact: Erin Halon |  | Needed Components: cover letter (required), Application (typical), and supporting documents: USACE approved Delineation, 106 coordination, ENG Form 4345, PCN form
Est. Permit Timeline
DSC Review date: 2/28/2012
Application Submitted: 3/14/2012
Duration of Review (Total): 135 days
1) Completeness (days): 30 days
2) Analysis (days): 45 days
3) other step (days): 60 days consult w/ FWS
4) Public Review (days): NA
5) other step (days): NA
Expected Date of Issue: approx. 7/27/2012 |  | Expected Date of Expiration/ Duration of Permit: |  |  | NA
Construction Monitoring Req.: No
Construction Restoration Req.: Yes
Post Occupancy Mitigation Req.: No
Notes: All impacts to USCAE features is temporary therefore site must be restored but no compensatory mitigation will be required. If we consult with FWS and provide FWS concurance to the USACE then 60 days are dropped.
PERMIT: CWA Section 401
Permit Standard: RWQCB |  | Date of information: 1/30/2012 |  | Consultation Started: Not started
Issuing Agency: RWQCB Fresno District |  | Application Fee: | Yes | Amount of Fee: TBD based on volume of fill
Agency Contact: To be determined at submittal |  | Needed Components: cover letter (required), Application (typical), and supporting documents: Copy of USACE submittal packet
Est. Permit Timeline
DSC Review date: 2/28/2012
Application Submitted: 3/14/2012
Duration of Review (Total): 135 days
1) Completeness (days): 30 days
2) Analysis (days): 90 days
3) other step (days): 8/9/12 Board Approval
4) Public Review (days): NA
5) other step (days): 5 days after approval
Expected Date of Issue: 8/16/2012 |  | Expected Date of Expiration/ Duration of Permit: |  |  | 8/16/2013
Construction Monitoring Req.: No
Construction Restoration Req.: Yes
Post Occupancy Mitigation Req.: No
Notes: Board meets 2nd and 4th Thursdays of every month.
PERMIT:
Permit Standard: |  | Date of information: |  | Consultation Started:
Issuing Agency: |  | Application Fee: |  | Amount of Fee:
Agency Contact: |  | Needed Components: cover letter (required), Application (typical), and supporting documents:
Est. Permit Timeline
DSC Review date:
Application Submitted:
Duration of Review (Total):
1) Completeness (days):
2) Analysis (days):
3) other step (days):
4) Public Review (days):
5) other step (days):
Expected Date of Issue: |  | Expected Date of Expiration/ Duration of Permit:
Construction Monitoring Req.: Yes / No
Construction Restoration Req.: Yes / No
Post Occupancy Mitigation Req.: Yes / No
Notes:
PERMIT:
Permit Standard: |  | Date of information: |  | Consultation Started:
Issuing Agency: |  | Application Fee: |  | Amount of Fee:
Agency Contact: |  | Needed Components: cover letter (required), Application (typical), and supporting documents:
Est. Permit Timeline
DSC Review date:
Application Submitted:
Duration of Review (Total):
1) Completeness (days):
2) Analysis (days):
3) other step (days):
4) Public Review (days):
5) other step (days):
Expected Date of Issue: |  | Expected Date of Expiration/ Duration of Permit:
Construction Monitoring Req.: Yes / No
Construction Restoration Req.: Yes / No
Post Occupancy Mitigation Req.: Yes / No
Notes: