United States Department of the Interior

NATIONAL PARK SERVICE

DENVER SERVICE CENTER

12795 W. Alameda Parkway

P.O. Box 25287

Denver, Colorado 80225-0287

IN REPLY REFER TO:

D5217 (DSC-CS)

PARK-PMIS

1443C_____

# LETTER OF SUBSTANTIAL COMPLETION

Contractor

Address

City, State Zip

Gentlemen:

Reference:	Park, _____ County, State, Contract No. 1443C_____, Developed Area, Project Title, Package No. PARK-PMIS

Subject:	Letter of Substantial Completion

An inspection of the work on the above referenced contract was conducted on Date.  Those participating were Mr. ______, representing _____; Messrs. ___________ representing _____; and Messrs. _______ representing the National Park Service.

The inspection revealed that the work has been completed substantially in accordance with the plans and specifications and is accepted as of  DATE, YEAR, subject to the terms and conditions of the contract and subject to the satisfactory completion of the following items, which remain to be accomplished:

| Item | # Description | ## Price |
| --- | --- | --- |
|  | # BUILDING A – NEW BUNKHOUSE |  |
|  | Paint between all doubled rafter ends. | $500.00 |
|  | Caulk rafter ends – daylight still shows through. | $200.00 |
|  | Install thresholds | $300.00 |
|  | Paint ventwells | $50.00 |
|  | Paint condenser control box and copper tube brown. | $100.00 |
|  | Redo side backsplash on vanity in east bedroom to match other one. | $100.00 |
|  | Caulk side backsplash on vanity in west bedroom | $25.00 |
|  | Clean glue/caulk from rafter above exterior door in west bedroom. Revarnish. | $100.00 |
|  | Linoleum buckled between kitchen and bedroom | $400.00 |
|  | Bubble in bedroom linoleum to the west of bedroom door. | $400.00 |
|  | # CRAWL SPACE |  |
|  | Install rodent barrier around all penetrations of floor. | $250.00 |
|  | Grout all stemwall penetrations. | $150.00 |
|  | # GENERAL |  |
|  | Provide Operation and Maintenance Manuals. | $1,500.00 |
|  | Furnish project record drawings. | $1,500.00 |
|  | # Remove all temporary electric service to site, including overhead lines. | $500.00 |
|  | # Remove office trailer. | $1,000.00 |
|  | # Perform final clean-up of site. | $450.00 |
|  | # TOTAL | $7,525.00 |

The punch list work shall be completed as soon as possible, but no later than _______ (refer to spec. Sec. 01770, usually 30 days), days, unless weather impacts prevent the completion.  In accordance with Division 1 of the project specifications, if the work is not completed by that time, the Government may either replace or correct the work with an appropriate reduction in the contract price or charge for re-inspection costs in accordance with the Inspection of Construction clause of the contract.

Your work will continue to be coordinated and scheduled with onsite representative Mr/Ms __________.

Sincerely,

CO NAME

Contracting Officer

bcc:

Regional Director, _____ Region

Supt., _____ SO

Supt., _____

DSC-PM, _____

CS0202:CSpecialist:ext:pt:date:SubstantialCompletion.doc