NPS DSC Division 1 Specifications

National Park Service (NPS) - Denver Service Center (DSC) | 9-10-25

By using NPS DSC Division 1 Specifications, you acknowledge you read, understand,
and will format edits according to NPS DSC Division 1 Specifications Instructions.

<Insert Park and Project Management Information System (PMIS) number>

SECTION 01 31 00 - PROJECT MANAGEMENT AND COORDINATION

GENERAL

SUMMARY

Section includes administrative provisions for coordinating construction operations on Project including, but not limited to, the following:

Adjust list to suit Project.

Definitions

Construction Coordination

Submittals

Coordination Drawings

Requests for Information (RFIs)

NPS Project Management and Communication Software

Project Meetings

Environmental Coordination

Permits

Related Requirements:

Retain subparagraphs below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

Section 01 32 16 "Construction Schedule" for preparing and submitting Construction Contractor’s construction schedule.

Section 01 73 40 "Execution" for procedures for coordinating general installation and field-engineering services, including establishment of benchmarks and control points.

Section 01 77 00 "Closeout Procedures" for coordinating closeout of the Contract.

Section 01 91 14 "Total Building Commissioning" for coordinating the work with Owner’s Commissioning Authority.

DEFINITIONS

Retain subparagraphs below that Contractor might expect to find in this Section.

Agency with Jurisdiction

Construction Permits – Contractor Provided

Government Furnished Permits

CONSTRUCTION COORDINATION

Requirements in this Article expand requirements in the General Conditions. Delete if General Conditions suit Project requirements and specific actions required.

Coordination:  Coordinate construction operations included in different Sections of Specifications to ensure efficient and orderly installation of each part of the Work. Coordinate construction operations, included in different Sections, which depend on each other for proper installation, connection, and operation.

Schedule construction operations in sequence required to obtain best results where installation of one part of the Work depends on installation of other components, before or after its own installation.

Coordinate installation of different components with other Construction Contractors to ensure maximum accessibility for required maintenance, service, and repair.

Make provisions to accommodate items scheduled for later installation.

Where availability of space is limited, coordinate installation of different components to ensure maximum performance and accessibility for required maintenance, service, and repair of components, including mechanical and electrical.

Properly plan construction operations to include permit requirements.  Allow enough time to execute permit provisions to maintain work schedule, site visits, inspections, and reporting deadlines.

Prepare memoranda for distribution to each party involved, outlining special procedures required for coordination.  Include such items as required notices, reports, and list of attendees at meetings.

Administrative Procedures: Coordinate scheduling and timing of required administrative procedures with other construction activities and activities of other Construction Contractors to avoid conflicts and to ensure orderly progress of the Work. Such administrative activities include, but are not limited to:

Preparation of Construction Contractor Construction Schedule

Preparation of the Schedule of Values

Installation and removal of temporary facilities and controls

Delivery and processing of submittals

Progress meetings

Permit requirements

Pre-installation conferences

Project closeout activities

Commissioning activities

SUBMITTALS

Delete requirement for Coordination Drawings (A-C) below if installation is completely shown on Shop Drawings. Coordinate with individual Sections.

Coordination Drawings: Prepare Coordination Drawings if limited space availability necessitates maximum utilization of space for efficient installation of different components or if coordination is required for installation of products and materials fabricated by separate entities.

Content: Project-specific information, drawn accurately to scale. Do not base Coordination Drawings on reproductions of Contract Documents or standard printed data. Include following information, as applicable:

Indicate functional and spatial relationships of components of architectural, structural, civil, mechanical, and electrical systems.

Indicate dimensions shown on Contract Drawings and make specific note of dimensions that appear to be in conflict with submitted equipment and minimum clearance requirements.  Provide alternate sketches to Contracting Officer (CO) for resolution of such conflicts.

Indicate space requirements for routine maintenance and anticipated replacement of components during the life of the installation.

Show location and size of access doors required for access to concealed dampers, valves, and controls.

Indicate required installation sequences.

Refer to individual Sections for Coordination Drawing requirements for Work in those Sections.

Follow NPS DSC Electronic Drawing Standards. See CAD/BIM (Computer Aided Design/Building Information Modeling) & Drafting Standards page > DSC Requirements section.

Coordination Drawing Organization: Organize coordination drawings as follows:

Floor Plans and Reflected Ceiling Plans: Show architectural, structural, mechanical, plumbing, fire-protection, fire-alarm, and electrical elements. Show locations of visible ceiling-mounted devices relative to acoustical ceiling grid.  Supplement plan drawings with section drawings where required to adequately represent the Work.

Plenum Space: Indicate sub-framing for support of ceiling and wall systems, mechanical and electrical equipment, and related Work. Locate components within ceiling plenum to accommodate layout of light fixtures indicated on Drawings. Indicate areas of conflict between light fixtures and other components.

Mechanical Rooms: Provide coordination drawings for mechanical rooms showing plans and elevations of mechanical, plumbing, fire-protection, fire-alarm, and electrical equipment.

Structural Penetrations: Indicate penetrations and openings required for all disciplines.

Slab Edge and Embedded Items: Indicate slab edge locations and sizes and locations of embedded items for metal fabrications, sleeves, anchor bolts, bearing plates, angles, door floor closers, slab depressions for floor finishes, curbs and housekeeping pads, and similar items.

Mechanical and Plumbing Work:

Sizes and bottom elevations of ductwork, piping, and conduit runs, including insulation, bracing, flanges, and support systems.

Dimensions of major components, such as dampers, valves, diffusers, access doors, cleanouts and electrical distribution equipment.

Fire-rated enclosures around ductwork.

Electrical Work:

Runs of vertical and horizontal conduit 1-1/4 inches (32 millimeters) in diameter and larger.

Light fixture, exit light, emergency battery pack, smoke detector, and other fire-alarm locations.

Panel board, switch board, switchgear, transformer, busway, generator, and motor control center locations.

Location of pull boxes and junction boxes, dimensioned from column center lines.

Fire-Protection System:

Locations of standpipes, mains piping, branch lines, pipe drops, and sprinkler heads.

Review: Contracting Officer will review coordination drawings to confirm Work is being coordinated; details of coordination are Construction Contractor's responsibility. If the Contracting Officer determines coordination drawings are not prepared in scope or detail, or are otherwise deficient, the Contracting Officer will inform Construction Contractor, who shall make changes and resubmit.

Retain "Coordination Drawing Prints" subparagraph below if submittal of prints is adequate for review of coordination drawings and electronic file submittal for review or record is not required.

Coordination Drawing Prints: Prepare coordination drawing prints according to requirements in Section 01 33 23 "Submittal Procedures."

Retain "Coordination Digital Data Files" paragraph below and delete "Coordination Drawing Organization" paragraph above if requiring electronic files for coordination drawings submittal for review and for record.

Coordination Digital Data Files: Prepare coordination digital data files according to:

Retain one of two "File Preparation Format" subparagraphs below.

File Preparation Format: Same digital data software program, version, and operating system as original Drawings.

File Submittal Format:  Submit or post coordination drawing files using Portable Document Format (PDF) file format.

Revise subparagraph below to reflect office practice for release of electronic files for use by Contractor.

Contracting Officer will furnish Construction Contractor one set of digital data files (AutoCad.dwg) of Drawings for use in preparing coordination digital data files.

Contracting Officer makes no representations as to accuracy or completeness of digital data files as they relate to Drawings.

Digital Data Software Program: Drawings are available in AutoCad.dwg.

Division 1 submittals required prior to mobilization:

Letter designating Project Superintendent

Construction Baseline Schedule

A Comprehensive Schedule of Values

Accident Prevention Plan

A List of Subcontractors for this project

Written statements from Subcontractors certifying compliance with applicable labor standard clauses.

Certificates of Insurance and Standard Form SF1413 for Contactor and all Subcontractors

Waste Management Plan

Quality Control Plan

Temporary Storm Water Pollution Prevention Plan (SWPP or UPPP)

Historic Preservation Treatment Plan (HPTP) (when applicable)

List of Required Construction Permits (when applicable). Include the following information for each permit:

Name of Permit

Agency(ies) with Jurisdiction issuing the permit

Information required from the Government to complete permit application

REQUESTS FOR INFORMATION (RFIs)

Revise to suit Project, special NPS requirements, and office practice.

General: Immediately on discovery of the need for additional information or interpretation of Contract Documents, Construction Contractor shall prepare and submit an RFI utilizing form created on NPS project management and communication software.

Contracting Officer will not respond to RFIs submitted by other entities controlled by Construction Contractor.

Coordinate and submit RFIs in a prompt manner to avoid delays in the work.

If needed, insert requirements to define frivolous RFIs. Some owners and design professionals include a provision that assesses cost of design professional's time and materials to Contractor for unnecessary or frivolous RFIs.

Content of RFI: Include detailed, legible description of item needing information or interpretation and the following:

RFI number, numbered sequentially

Date

RFI subject

Specification Section number and title and related paragraphs, as appropriate.

Drawing number and detail references, as appropriate.

Field dimensions and conditions, as appropriate.

Construction Contractor's suggested resolution: If suggested resolution impacts Contract Time or Contract Sum, Construction Contractor shall state impact in RFI.

Construction Contractor's signature

Requested date for response

Attachments: Include sketches, descriptions, measurements, photos, Product Data, Shop Drawings, coordination drawings, and other information necessary to fully describe items needing interpretation.

Include dimensions, thicknesses, structural grid references, and details of affected materials, assemblies, and attachments on attached sketches.

Delete below if NPS/DSC Project Website is not used.

RFI Form: Complete and submit on NPS project management and communication software.

Contracting Officer’s Action: Contracting Officer will review each RFI, determine action required, and respond. The Contracting Officer will determine the critical nature of each RFI and issue response accordingly.

The following are not considered to be RFIs and will receive no action:

Requests for approval of submittals.

Requests for approval of substitutions.

Requests for approval of Construction Contractor's means and methods.

Requests for coordination information already indicated in Contract Documents.

Requests for adjustments in Contract Time or Contract Sum.

Requests for interpretation of Architect's actions on submittals.

Incomplete RFIs or inaccurately prepared RFIs.

Contracting Officer's action may include a request for additional information; time for response will date from time of receipt of additional information.

Contracting Officer's action on RFIs may result in need for a change to Contract Time or Contract Sum. All contract changes will be processed according to the terms and conditions of the contract.

PROJECT MANAGEMENT AND COMMUNICATION SOFTWARE

Retain if Contractor is required to use. Revise to suit Project.

Use to manage project communication and document sharing during contract period on:

Project directory

Project correspondence

Meeting agendas and minutes

Contract modifications forms and logs

RFI form and processing

Task and issue management

Photo documentation

Baseline schedule, schedule updates and calendar management

Submittal form and processing

Payment coordination documentation

Reminder and tracking functions

Archiving functions

Notification of submittal and RFI statuses and current responsible party

Permits and addendums

Some documents are not suitable to be shared using NPS project management and communication software. Documents containing Personal Identifying Information (PII) (i.e. certified payrolls) shall not be shared and shall be coordinated with the project team as appropriate.

Review product descriptions for packages in first paragraph below; revise to suit Project. Not all software packages listed below offer all Project website features described in paragraphs above.

Revise paragraph below if Architect’s instruments of service posted on Project website are not covered by another data licensing agreement. Coordinate with provisions of Owner/Architect Agreement and Supplementary Conditions.

PROJECT MEETINGS

Preconstruction Conference: Before the start of construction, the Contracting Officer will arrange an on-site meeting with Construction Contractor. Meeting agenda will include the following as a minimum:

Roles & Responsibilities / Lines of Authority

Park rules and regulations

Jobsite Safety

Resolution of comments on required Division 1 documents

Coordination of Subcontractors

Labor law application

Modifications

Payments to Construction Contractor

Payroll reports

Contract time

Liquidated damages

Construction Contractor Performance Evaluation

Display of Hotline posters

Notice to proceed

Correspondence procedures

NPS project management and communication software

Acceptance/rejection of work

Progress meetings

Submittal procedures

NPS Final Accessibility Inspection

Environmental requirements

Permit requirements

As-constructed drawings/operation and maintenance (O&M) manuals.

Saturday, Sunday, holiday and night work.

Reference materials

Value engineering

Schedule of Values

Progress Meetings: Contracting Officer will schedule weekly meetings with Construction Contractor.

Attendees: In addition to Government Representatives, each Construction Contractor, Subcontractor, supplier, and other entity concerned with current progress or involved in planning, coordination, or performance of future activities shall be represented. Participants at meetings shall be familiar with the Project and authorized to conclude matters relating to the Work.

Agenda: Review and correct or approve minutes of previous progress meeting. Review other items of significance that could affect progress. Meeting agenda will include:

Approval of minutes of previous meetings

Submittal status

Review of off-site fabrication and delivery schedules.

Requests for information (RFI) and other issues.

Modifications

Work in progress and projected.

Status of required inspections (Special Inspections, Accessibility, etc.)

Inspections of work in progress and projected (Special inspections, Accessibility, etc.)

Construction Schedule update (provide updated Critical Path Method (CPM)).

Status of Project Record Drawings and O&M manuals.

Other business relating to work.

Permit requirements

Preinstallation Conferences: Conduct at Project site before each construction activity that requires coordination with other construction.

Attendees: Installer and representatives of manufacturers and fabricators involved in or affected by installation and its coordination or integration with other materials and installations that have preceded or will follow shall attend meetings. Advise the Contracting Officer of scheduled meeting dates.

Agenda: Review progress of other construction activities and preparations for particular activity under consideration, including requirements for:

Contract Documents

Options

Related RFIs

Related Change Orders

Purchases

Deliveries

Submittals

Review of mockups

Possible conflicts

Compatibility requirements

Time schedules

Weather limitations

Manufacturer's written instructions

Warranty requirements

Compatibility of materials

Acceptability of substrates

Temporary facilities and controls

Space and access limitations

Regulations of agency(ies) with jurisdiction

Testing and inspecting requirements

Installation procedures

Coordination with other work

Required performance results

Protection of adjacent work

Protection of construction and personnel

Record significant conference discussions, agreements, and disagreements, including required corrective measures and actions.

Reporting: Distribute minutes of meetings to each party present and to other parties requiring information.

Do not proceed with installation if the conference cannot be successfully concluded.  Initiate whatever actions are necessary to resolve impediments to the performance of Work and reconvene the conference at the earliest feasible date.

ENVIRONMENTAL COORDINATION

Construction Contractor’s Environmental Manager: Designate on-site party responsible for overseeing Construction Contractor’s conformance to environmental goals for project and implementing procedures for environmental protection.

Qualifications: Minimum 3 years Construction experience on projects of similar size and scope; with environmental procedures similar to this project; [familiarity with Environmental Management Systems (EMSs) such as International Organization for Standardization (ISO) 14001]; familiar with environmental regulations applicable to construction operations.

Responsibilities: Responsibilities shall include:

Edit the following for project specific requirements

Compliance with applicable Federal, State, and local environmental regulations, including maintaining required documentation.

Implementation of Waste Management Plan (WMP).

Implementation of Indoor Air Quality (IAQ) Management Plan.

Implementation of Storm Water Pollution Prevention Plan (SWPPP).

Present overview of environmental issues and summarize site specific procedures relating to management plans at Preconstruction conference.

Training for Construction Contractor personnel in accordance with position requirements.

Monitoring and documentation of environmental procedures.

Perform project quality control in accordance with requirements specified in Related Sections, including:

Quality Requirements

Regulatory Requirements

Indoor Air Quality (IAQ) Management

Noise and Acoustics Management

Temporary Storm Water Pollution Prevention Environmental Management

Construction Waste Management

Construction Contractor’s Environmental Training Program: Construction Contractor shall provide environmental training for workers performing work on project site. Training shall include:

Overview of environmental issues related to building industry.

Overview of environmental issues related to Project.

Review of site-specific procedures and management plans:

Construction Waste Management

Indoor Air Quality (IAQ) Management

Noise and Acoustics Management

Temporary Storm Water Pollution Prevention

Pollution prevention (P2) means "source reduction," as defined under the Pollution Prevention Act and other practices that reduce or eliminate creation of pollutants. United States Environmental Protection Agency (US EPA) and other organizations administer a variety of Pollution Prevention (P2) practices, initiatives, and programs.

Site Disturbance One Acre and Less: Contractor shall provide evidence of participation in P2 programs.

Site Disturbance Greater Than One Acre: Contractor shall provide evidence of participation in P2 programs and shall provide evidence of P2 training in accordance with US EPA programs.

Pollution Prevention (P2) practices: Submit evidence of [P2 training] [participation in

P2 programs] [familiarity with P2 practices].

Compliance with environmental regulations: As specified in Regulatory Requirements. Submit Construction Contractor 40 CFR (Code of Federal Regulations) employee training records upon request of the Contracting Officer.

Where violation of environmental procedures requirements will irreversibly damage the site, identify requirements for documentation of progress at specific intervals.

Provide documentation for environmental procedures as specified herein and in accordance with the approved Waste Management Plan, IAQ Management Plan, and Storm Water Pollution Prevention Plan.

PERMITS

General:

Permits and Responsibilities: Construction Contractor shall, without additional expense to the Government, be responsible for obtaining necessary licenses and permits, and for complying with Federal, State and municipal laws, codes, and regulations applicable to the performance of the work. Construction Contractor shall also be responsible for damages to persons or property that occur as a result of Construction Contractor’s fault or negligence; and for materials delivered and work performed until completion and acceptance of the work.

For the purpose of this contract, Construction Contractor will not be considered an agent of the Government. Construction Contractor shall comply with appropriate Federal, State and local laws.

If there are no Government-Furnished Permits, delete paragraphs and subparagraphs below. Consult with NPS and list all permits acquired in design process. Provide permit type, identification number and Agency(ies) with Jurisdiction.

Government Furnished Permits: During development of the project’s design, permits listed below were negotiated and agreed to by the Government. Terms and provisions of these permits shall be adhered to for the duration specified in each permit.

A permit was acquired for <Insert type> with identification number <Insert ID Number>.  The Agency(ies) with Jurisdiction for this permit is <Insert Agency(ies) with Jurisdiction>.

If no construction permits required, delete paragraphs and subparagraphs below. Determine permit requirements for project and list type and Agency(ies) with Jurisdiction.

Potential Permits: Permits listed below were identified during the design process as likely to be required based on typical means and methods of construction. The list is provided to assist Construction Contractor in determining which permits will be required for contract’s chosen means and methods. The list shall not be considered complete; it is the Construction Contractors’ responsibility to determine means and methods and obtain required permits. Construction Contractor shall obtain all permits required to legally conduct work.

Review permits issued, both government-provided and those obtained by Contractor. Ensure precautions have been taken to fully comply with permit provisions, including material, meetings, reporting and anything necessary for work to be accomplished on schedule. Edit list below accordingly.

Electrical Utility Hookup - <Insert Agency(ies) with Jurisdiction>

Gas Utility Hookup - <Insert Agency(ies) with Jurisdiction>

Sewer Hookup - <Insert Agency(ies) with Jurisdiction>

New Water Meter - <Insert Agency(ies) with Jurisdiction>

Construction trailer, Utilities hookup permit - <Insert Agency(ies) with Jurisdiction>

New Stationary Air Pollution Source - <Insert Agency(ies) with Jurisdiction>

Street Closure - <Insert Agency(ies) with Jurisdiction>

Stormwater Pollution Prevention Permit - <Insert Agency(ies) with Jurisdiction>

MS4 Stormwater Permit - <Insert Agency(ies) with Jurisdiction>

Dewatering Permit - <Insert Agency(ies) with Jurisdiction>

Coordination with Agency(ies) with Jurisdiction Issuing Permits

Coordination: Contact the Agency(ies) with Jurisdiction as needed and sufficiently in advance to avoid delaying work: Coordinate meetings, reporting requirements, inspections, and other requirements.

Administrative Procedures:

Coordinate scheduling and timing of required administrative provisions of project permits with Agency(ies) with Jurisdiction, Construction Manager, and Park to avoid conflicts.

Supply needed information to Agency(ies) with Jurisdiction issuing permits, pay fees required and provide material needed to comply with permit’s conditions and provisions.

Upload permits to NPS project management and communication software when permits are obtained.

PRODUCTS (Not Used)

EXECUTION (Not Used)

END OF SECTION 01 31 00