## Template
NPS CONSTRUCTABILITY CHECKLIST For instructions, see Instructions tab below. ¦ 9-27-16
PARK: | PROJECT TITLE: | PMIS: (Project Management Information System) | DATE: | DBB or DB (Design-Bid-Build or Design-Build) | COMPLETED BY:
ITEM # | PROJECT ISSUES | SD COMMENTS Schematic Design |  | DD or RFP COMMENTS Design Development (DBB) OR Request for Proposal (DB) |  | CD or RFP RESOLUTION Construction Documents (DBB) OR Request for Proposal (RFP)
PROJECT INTRODUCTION
1 | ANY NON-TYPICAL CONTRACT LINE ITEMS OR MISCELLANEOUS CONTRACT CONCERNS
2 | RECOMMENDED CONTRACT LENGTH; SEASONAL BREAKS IN CONTRACT; IDENTIFY CONTRACT TIMING ISSUES THAT NEED TO BE ADDRESSED; IDENTIFY SPECIFIC PHASING REQUIREMENTS
PERMITTING & COMPLIANCE
3 External Permit or Approval | LIST REQUIRED GOVERNMENT FURNISHED PERMITS AND APPROVALS: List by Agency-Type: Example: USACE-CWA404 NWP18. Include contact, and phone number.
4 External Permit or Approval | LIST REQUIREMENTS FOR GOVERNMENT FURNISHED PERMITS: Include inspections, meetings, close out requirements, and drawings.
5 External Permit or Approval | LIST REQUIRED CONSTRUCTION CONTRACTOR FURNISHED PERMITS AND APPROVALS
6 External Permit or Approval | DESCRIBE WHERE AND HOW PERMIT REQUIREMENTS ARE INCLUDED IN DESIGN PACKAGE: For each permit, describe requirement, specification (section and paragraph) and/or drawing number.
7 Internal Compliance | IDENTIFY COMPLIANCE REQUIREMENTS: SHPO, NEPA, EA: List requirement, status, and date or expected date.
8 Internal Compliance | COMPLETE ALL APPROVALS: Director's, DAB, Congressional Funding issues, estimate within available funds? Adequate time to complete work within project and funding constraints?
9 General | IDENTIFY REQUIRED SPECIAL INSPECTIONS: List inspecting or approving organization and reason required.
STAGING AND MOBILIZATION
10 | IDENTIFY AREAS FOR STAGING INCLUDING AREAS FOR PRIME, SUBS, MATERIAL, AND PARKING; IDENTIFY AREAS FOR CONSTRUCTION CAMP IF APPLICABLE: List drawing number(s) showing staging area(s).
11 | IDENTIFY TEMPORARY UTILITIES AVAILABLE FOR CONSTRUCTION: List drawing number or specification section that indentifies available utilities-electrical, phone, non-potable and potable water, sanitary-provider, meter needed, and responsible cost party.
12 | IDENTIFY CONSTRUCTION LOGISTICS: List drawing numbers that show traffic control, access restrictions, work hour restrictions, bridges, features, other.
13 | IDENTIFY IMPACTS TO PARK AND VISITOR OPERATIONS: List drawing number(s) or specification section(s) that identifies impacts (e.g. Visitor Impacts, Neighborhood-Urban Impacts, Detours, Closures).
14 | IDENTIFY SITE ACCESS ISSUES: List drawing number(s) or specification section(s) that identify issues (e.g. remote and road type constrained sites, weather closure restrictions, road and bridge load limits, road and tunnel height restrictions, crane and helicopter requirements).
SUBMITTALS
15 | LIST MATERIAL SUBMITTALS ON CRITICAL PATH; FOR DESIGN-BUILD (DB), LIST MATERIAL SUBMITTALS REQUIRING GOVERNMENT APPROVAL
16 | LIST LONG LEAD ITEMS; MATERIAL AND EQUIPMENT AVAILABILITY CONCERNS, SPECIAL DELIVERY REQUIREMENTS
17 | LIST OF SOLE SOURCE MATERIALS AND GOVERNMENT FURNISHED MATERIALS OR EQUIPMENT
SITE LAYOUT / RESOURCE PROTECTION
18 | TYPES OF RESOURCE PROTECTION REQUIRED: List where and how requirements are included in design package.
19 | ACCURATE SURVEY DATA ON PLANS: BMs, TBMs, TOPO
20 | PRELIMINARY SITE INVESTIGATION COMPLETE, EXISTING CONDITIONS VERIFIED AND INCLUDED IN PACKAGE
21 | CONSTRUCTION LIMITS CLEARLY SHOWN AND DEFINED FOR BOTH ACCESS AND CONSTRUCTION: List where and how requirements are included in design package.
22 | SPECIAL SIGNAGE REQUIREMENTS: Describe and list where requirements are included in design package.
23 | LIST WORK SAFETY CONCERNS, LOCATION, AND NEEDS: Include Height, Weather, Animal, Aerial, Public Accessibility, Security, Confined Space, Pathologic, Atmospheric, and others.
DEMOLITION
24 | ALL EXISTING UTILITIES LOCATED AND ACCURATELY SHOWN: Describe where shown.
25 | TEMPORARY SYSTEMS REQUIRED: Identify for Park or Public: Access, power, water, sanitary, covered access, exhibit relocation, movement assistance, accessibility.
26 | SALVAGE, RECYCLING, STORAGE, AND DISPOSAL REQUIREMENTS: Who is removing salvageable equipment and where requirements are included in design package?
27 | NOISE / DUST / SAFETY CONCERNS FOR PUBLIC OR ENVIRONMENT: Describe where included in design package.
28 | CONSTRAINTS ON MEANS AND METHODS: Blasting, Burning, Tidal, Weather, Public Accessibility, Existing structures/features, Holidays and Seasonal, Permitting, other.
29 | HAZARDOUS MATERIAL CONSIDERATIONS DEMO METHODS AND DISPOSAL STATE AND LOCAL REQUIREMENTS: Describe hazardous materials being addressed, how, and where in design package.
30 | ARCHEOLOGICAL MONITORING REQUIREMENTS: Describe what is needed and where in design package. Identify who provides monitor.
CONSTRUCTION
31 | MATERIAL, EQUIPMENT, LABOR AVAILABILITY FOR REMOTE SITES: Describe issues and where included in design package.
32 | SITE ACCESS RESTRICTIONS TO CONSTRUCTION OPERATIONS IF DIFFERENT OR MORE SUBSTANTIAL THAN ITEMS 12 AND 14
33 | ANTICIPATED WEATHER CONSIDERATIONS, CONSTRUCTION SEASON, OPTIMUM TIME TO ADVERTISE, RECOMMENDED CONTRACT LENGTH
34 | PARK / CONCESSION IMPOSED RESTRICTIONS INCLUDED IN DESIGN PACKAGE AND IMPACTS ON SCHEDULE & COST
35 | DESCRIBE FULL SCOPE OF WORK FOR LOCAL UTILITY COMPANIES AND CONSTRUCTION CONTRACTOR FOR EACH UTILITY
36 | DESCRIBE DISRUPTION REQUIREMENTS FOR UTILITY CONNECTIONS, CLOSURES, AND MAXIMUM ALLOWABLE INTERRUPTIONS: Describe where addressed in design package.
37 | SPECIFIC PHASING REQUIREMENTS: Detail what and where where provided in design package.
38 | DESCRIBE SPECIALIZED MATERIALS/INSTALLATION METHODS CERTIFICATIONS/TRAINING REQUIREMENTS
39 | COORDINATION WITH PARK OR CONCESSIONAIRE ON BENEFICIAL OCCUPANCY: Grand opening, fixed completion dates, etc.
40 | ADJACENT or CONCURRENT CONTRACTS COORDINATION / OVERLAPS ON CONCURRENT OR FUTURE CONTRACTS
41 | VALUE ENGINEERING POTENTIAL
PROJECT CLOSEOUT
42 | TRAINING REQUIREMENTS, CERTIFICATIONS SPECIFIED
43 | OPERATION & MAINTENANCE (O&M) REQUIREMENTS
44 | LIST PERMITS NEEDING CLOSURE AND POINTS OF CONTACT: Describe requirement; include specification and/or drawing location for each.
45 | POST CONSTRUCTION REQUIREMENTS
46 | LIST LONG TERM MAINTENANCE NEEDS AND LOCATION IN THE DESIGN PACKAGE.

## Instructions
INSTRUCTIONS FOR NPS CONSTRUCTABILITY CHECKLIST
Introduction - The Constructability Checklist is to be used as a tool to inspire, document, track, and record project issues as they are discussed and resolved throughout preparation of the Design Development (DD), Construction Documents (CD), and Request for Proposal (RFP) documents. The end result is a completed checklist that identifies project issues and provides the background necessary to complete the contract documents (primarily Division 01 Specifications).
TITLE BLOCK - Complete the title block by filling in the Park, Project Title, PMIS number, Date, if DBB or DB (Design-Bid-Build (DBB) or Design (DB)), and Completed By in the appropriate column.
PROJECT ISSUES COLUMN - Typical constructability issues have been listed under the column title Project Issues. Insert additional issues as needed to cover project issues that are not already listed. If issues are listed that do not apply, insert N/A. Project issues are organized to coincide with the award and construction phasing of a project. They are organized under headings that are typically used as summary headings in a project schedule. If these project issues have significant impact on time, the impacts should be shown in a projected construction schedule developed during design. This is an effective way to accomplish construction planning, develop realistic expectations, and account for the time and cost implications of project issues.
SD COMMENTS COLUMN - Complete the necessary research to gain a full understanding of the project issues that will need to be considered. Explain in general what the specific issue is under the SD Comments (Schematic Design) column for each project issue.
DD COMMENTS / RFP COMMENTS COLUMN - Develop the necessary in-depth research to gain a full understanding of the project issues that will need to be considered. Explain in general what the specific issue is under the DD Comments (Design Development) / RFP Comments (Request for Proprosal) column for each project issue.
CD RESOLUTION / RFP RESOLUTION COLUMN - Develop a strategy on how each project issue will be resolved contractually. Indicate how it will be resolved under the CD Resolution (Construction Documents) / RFP Resolution (Request for Proprosal) column. Refer to specification or drawing where information is contained. Be as complete as possible. Be specific with language needed to describe a constraint, requirements for specific phasing, potential impacts to cost and schedule, etc.
General - After completing this checklist, make sure the resolution to the project issues have been incorporated into the CDs / RFPs. The Park, Project Manager (PM), and others may be responsible for some items and this should be so noted.