## Pay Estimate Form
| Pay Estimate Form National Park Service (NPS) - Denver Service Center (DSC) ¦ 7-27-17 | [7 empty] | IPP Invoice Number:
Invoice Date:
NAME OF PARK
PARK - PMIS
Pay Estimate Number: |  |  | Performance Period |  | thru |  |  |  | 14-Day Prompt Payment |  | 30-Day Final Payment
Contract Award Date |  |  | Initial Contract Calendar Days To Complete |  | Revised Contract Calendar Days To Complete |  | 0 | Notice To Proceed Date |  | Number of Contract Calendar Days Elapsed |  | 0
Contract #: |  |  |  |  | Original Contract Completion Date: |  |  | 0 | Revised Completion Date: |  | 0
Contractor: |  | Name, address, phone number | [6 empty] | Original Contract Amount:
Project: |  | Description of project | [6 empty] | Total Change Orders:
Location: |  | Park name, County, State | [6 empty] | Revised Contract Amount: |  | 0
Price Schedule Contract Line Item Number (CLIN) |  | DESCRIPTION |  |  | CONTRACT QUANTITY |  | UNIT PRICE | TOTAL CONTRACT PRICE FOR LINE ITEM | QUANTITY-TO-DATE or PERCENT COMPLETE | AMOUNT PAYABLE TO DATE
[5 empty] | Qty | Unit |  |  | (Choose proper format)
| 1 | [6 empty] | 0 | 0% | 0
| 2 | [6 empty] | 0 | 0 | 0
| 3 | [6 empty] | 0 | 0 | 0
| 4 | [6 empty] | 0 | 0 | 0
| 5 | [6 empty] | 0 | 0 | 0
| 6 | [6 empty] | 0 | 0 | 0
| 7 | [6 empty] | 0 | 0 | 0
| 8 | [6 empty] | 0 | 0 | 0
| 9 | [6 empty] | 0 | 0 | 0
| 10 | [6 empty] | 0 | 0 | 0
| 11 | [6 empty] | 0 | 0 | 0
| 12 | [6 empty] | 0 | 0 | 0
| 13 | [6 empty] | 0 | 0 | 0
| 14 | [6 empty] | 0 | 0 | 0
| 15 | [6 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
|  | Total | [5 empty] | 0
( * ) A single asterisk by the line number indicates a revised line item.
(**) A double asterisk by the line number indicates a new line item.
| Percent $ Complete (Total To Date / Rev Contract Amt) |  |  |  |  | #DIV/0! |  | SUMMARY
[8 empty] | Total To Date: |  | 0
| Percent Contract Construction Period Elapsed |  |  |  |  | #DIV/0! |  | Less: Retained Amount |  | 0
[8 empty] | Subtotal |  | 0
[8 empty] | Less: Previous Payments |  | 0
[8 empty] | Less: Liquidated Damages |  | 0
[8 empty] | AMOUNT DUE |  | 0
PRIME CONTRACTOR CERTIFICATION OF PAYMENTS TO SUBCONTRACTORS
Contractor: |  | Name, address, phone number | [8 empty] | Pay Estimate No. | 0
Contract No. |  | 0
Subcontractor' Name & Address |  |  |  | SF1413 Submitted? Y / N | Insurance Certificate Submitted? Y / N |  | Total Subcontract Amount | Previous Payments To Subcontractor | Subcontractor Payment Amount Included In Current Pay Estimate |  | Total Amount Paid
1 | [6 empty] | 0 | 0 | 0 |  | 0
2 | [6 empty] | 0 | 0 | 0 |  | 0
3 | [6 empty] | 0 | 0 | 0 |  | 0
4 | [6 empty] | 0 | 0 | 0 |  | 0
5 | [6 empty] | 0 | 0 | 0 |  | 0
6 | [6 empty] | 0 | 0 | 0 |  | 0
7 | [6 empty] | 0 | 0 | 0 |  | 0
8 | [6 empty] | 0 | 0 | 0 |  | 0
9 | [6 empty] | 0 | 0 | 0 |  | 0
10 | [6 empty] | 0 | 0 | 0 |  | 0
11 | [6 empty] | 0 | 0 | 0 |  | 0
12 | [6 empty] | 0 | 0 | 0 |  | 0
13 | [6 empty] | 0 | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 | 0 |  | 0
Total Subcontract Amount | [6 empty] | 0 | 0 | 0 |  | 0
Subcontractor Percentage of Total Contract Price | [6 empty] | #DIV/0! | Subcontractor Percentage of Total Contract Price To Date |  |  |  | #DIV/0!
Prime Contractor Percentage of Total Contract Price | [6 empty] | #DIV/0! | Prime Contractor Percentage of Total Contract Price To Date |  |  |  | #DIV/0!
PRIME CONTRACTOR CERTIFICATION
I hereby certify, to the best of my knowledge and belief certify that:
(1) |  | The amounts requested are only for performance in accordance with the specifications, terms and conditions of the contract;
(2) |  | All payments due to Subcontractors and Suppliers from previous payments received under the contract have been made, and timely payments will be made from the proceeds of the payment covered by this certification, in accordance with subcontract agreements and the requirements of Chapter 39 of Title 31, United States Code;
(3) |  | This request for progress payments does not include any amounts which the Prime Contractor intends to withhold or retain from a Subcontractor or Supplier in accordance with the terms and conditions of this subcontract; and
(4) |  | This certification is not to be construed as final acceptance of a Subcontractor's performance.
(5) |  | For Set-Aside contracts only - In accordance with Federal Acquisition Regulation (FAR) 52.219-14, 52.219-3, 52.219-3 with Alternative I, the Contractor is required to self-perform ______% of the actual work under this contract. If current % is less than the minimum requirements, the Contractor is required to submit a recovery plan to the Contracting Officer (CO). The Contractor has self-performed ______% of the contract amount to date. (Submit attached subcontracting plan worksheet to substantiate certification.)
Signature:
Name and Title:
Date:

## SAMPLE
| Pay Estimate Form SAMPLE National Park Service (NPS) - Denver Service Center (DSC) ¦ 7-27-17 | [7 empty] | IPP Invoice Number: |  | 52005142014
[9 empty] | Invoice Date: |  | 2013-07-15
Grand Canyon National Park
GRCA - 123456
Pay Estimate Number: |  | 2 | Performance Period | 2013-06-14 | thru | 2013-07-14 |  |  | 14-Day Prompt Payment | X | 30-Day Final Payment
Contract Award Date |  | 2013-05-01 | Initial Contract Calendar Days To Complete | 365 | Revised Contract Calendar Days To Complete |  | 365 | Notice To Proceed Date | 2013-05-14 | Number of Contract Calendar Days Elapsed |  | 61
Contract #: |  | C2014050140 |  |  | Original Contract Completion Date: |  |  | 2014-05-14 | Revised Completion Date: |  | 2014-05-14
Contractor: |  | ACME Construction, 123 Easy Street, Flagstaff, AZ 12345 | [6 empty] | Original Contract Amount: |  | 881000
Project: |  | Replacement of Housing Complex "A" | [6 empty] | Total Change Orders: | 2 | 75000
Location: |  | Grand Canyon National Park, Coconino County, AZ | [6 empty] | Revised Contract Amount: |  | 956000
Price Schedule Contract Line Item Number (CLIN) |  | DESCRIPTION |  |  | CONTRACT QUANTITY |  | UNIT PRICE | TOTAL CONTRACT PRICE FOR LINE ITEM | QUANTITY-TO-DATE or PERCENT COMPLETE | AMOUNT PAYABLE TO DATE
[5 empty] | Qty | Unit |  |  | (Choose proper format)
| 1 | Replace Housing Complex "A" |  |  | 1 | LS | 750000 | 750000 | 12.57% | 94275
| 2 | Option 1 - Resurface Spruce Road |  |  | 500 | LF | 200 | 100000 | 100 | 20000
| 3 | Option 2 - Paint Storage Facility |  |  | 1 | LS | 3500 | 3500 | 21.5% | 752.5
| 4 | Option 3 - Install Guard Rails |  |  | 100 | LF | 150 | 15000 | 15 | 2250
| 5 | Option 4 - Remove excess fill material |  |  | 500 | CY | 25 | 12500 | 25 | 625
** | 6 | Mod 2 - Add towpath from Housing Complex |  |  | 1 | LS | 75000 | 75000 | 10.15% | 7612.5
| 7 | [6 empty] | 0 | 0 | 0
| 8 | [6 empty] | 0 | 0 | 0
| 9 | [6 empty] | 0 | 0 | 0
| 10 | [6 empty] | 0 | 0 | 0
| 11 | [6 empty] | 0 | 0 | 0
| 12 | [6 empty] | 0 | 0 | 0
| 13 | [6 empty] | 0 | 0 | 0
| 14 | [6 empty] | 0 | 0 | 0
| 15 | [6 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
|  | Total | [5 empty] | 956000
( * ) A single asterisk by the line number indicates a revised line item.
(**) A double asterisk by the line number indicates a new line item.
| Percent $ Complete (Total To Date / Rev Contract Amt) |  |  |  |  | 13.13% |  | SUMMARY
[8 empty] | Total To Date: |  | 125515
| Percent Contract Construction Period Elapsed |  |  |  |  | 16.71% |  | Less: Retained Amount |  | 0
[8 empty] | Subtotal |  | 125515
[8 empty] | Less: Previous Payments |  | 0
[8 empty] | Less: Liquidated Damages |  | 0
[8 empty] | AMOUNT DUE |  | 125515
PRIME CONTRACTOR CERTIFICATION OF PAYMENTS TO SUBCONTRACTORS
Contractor: |  | ACME Construction, 123 Easy Street, Flagstaff, AZ 12345 | [8 empty] | Pay Estimate No. | 2
Contract No. |  | C2014050140
Subcontractor Name & Address |  |  |  | SF1413 Submitted? Y / N | Insurance Certificate Submitted? Y / N |  | Total Subcontract Amount | Previous Payments To Subcontractor | Subcontractor Payment Amount Included In Current Pay Estimate |  | Total Amount Paid
1 | "AAA" Asphalt, 123 1st St., Flagstaff, AZ |  |  | Y | Y |  | 100000 | 10000 | 10000 |  | 20000
2 | Bob & Bruce Painting, 234 2nd St., Globe, AZ |  |  | Y | Y |  | 3500 | 400 | 352.5 |  | 752.5
3 | Guard-Rails-R-Us, 345 3rd St., Phoenix, AZ |  |  | Y | Y |  | 1500 | 1000 | 1250 |  | 2250
4 | Ed's Trucking, 456 4th St., Springerville, AZ |  |  | Y | Y |  | 12500 | 300 | 325 |  | 625
5 | Landscapes USA, 567 5th St., Phoenix, AZ |  |  | Y | Y |  | 75000 | 5000 | 2612.5 |  | 7612.5
6 | Build-rite Mechanical, 678 6th St, Las Vegas, NV |  |  | Y | Y |  | 20000 | 3000 | 5000 |  | 8000
7 | "XYZ" Concrete, 789 7th St., Flagstaff, AZ |  |  | Y | Y |  | 100000 | 5000 | 7000 |  | 12000
8 | Arizona Excavating, 890 8th St., Flagstaff, AZ |  |  | Y | Y |  | 5000 | 8000 | 15000 |  | 23000
9 | [6 empty] | 0 | 0 | 0 |  | 0
10 | [6 empty] | 0 | 0 | 0 |  | 0
11 | [6 empty] | 0 | 0 | 0 |  | 0
12 | [6 empty] | 0 | 0 | 0 |  | 0
13 | [6 empty] | 0 | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 | 0 |  | 0
Total Subcontract Amount | [6 empty] | 317500 | 32700 | 41540 |  | 74240
Subcontractor Percentage of Total Contract Price | [6 empty] | 33.21% | Subcontractor Percentage of Total Contract Price To Date |  |  |  | 59.15%
Prime Contractor Percentage of Total Contract Price | [6 empty] | 66.79% | Prime Contractor Percentage of Total Contract Price To Date |  |  |  | 40.85%
PRIME CONTRACTOR CERTIFICATION
I hereby certify, to the best of my knowledge and belief that:
(1) |  | The amounts requested are only for performance in accordance with the specifications, terms and conditions of the contract;
(2) |  | All payments due to Subcontractors and Suppliers from previous payments received under the contract have been made, and timely payments will be made from the proceeds of the payment covered by this certification, in accordance with subcontract agreements and the requirements of Chapter 39 of Title 31, United States Code;
(3) |  | This request for progress payments does not include any amounts which the Prime Contractor intends to withhold or retain from a Subcontractor or Supplier in accordance with the terms and conditions of this subcontract; and
(4) |  | This certification is not to be construed as final acceptance of a Subcontractor's performance.
(5) |  | For Set-Aside contracts only - In accordance with Federal Acquisition Regulation (FAR) 52.219-14, 52.219-3, 52.219-3 with Alternative I, the Contractor is required to self-perform ______% of the actual work under this contract. If current % is less than the minimum requirements, the Contractor is required to submit a recovery plan to the Contracting Officer (CO). The Contractor has self-performed ______% of the contract amount to date. (Submit attached subcontracting plan worksheet to substantiate certification.)
Signature:
Name and Title: |  |  |  | Barrett Jackson, Senior Construction Manager, ACME Construction
Date: |  |  |  | 08/01/2013
Barrett Jackson