## READ ME
Permit Plan Form
The Permit Plan is part of a larger DSC permitting process, which consists of Scoping all required permits (Permit Assessment Form); Assigning permits to be either Government Furnished, Contractor Provided, or Park Acquired; Planning a clear path to acquire each Government Furnished Permits (Permit Plan Form); Develop complete and acceptable applications; and Acquire Government Furnished Permits prior to solicitation.
This workbook contains four tabs, including this READ ME tab. The "Template" tab is the blank work form to be used by the staff filling out the Permit Plan. The "Guidelines" tab is the Template with instructions and explanatory text. This tab is provided to staff to help them fill out the Permit Plan in a manner that will both answer the questions about permitting and integrate with DSC permitting procedures. The fourth tab, "Example," is a Permit Plan form that has been filled. The Permit Plan is meant to evolve as the project does. It also acts to capture efforts made in the pursuit of which permits will be required for a project.
For more information see: web link to be added once on DSC Workflows
Definitions:
• DSC - Denver Service Center
• Agency - Authority Having Jurisdiction
• List of All Permits - A list of the name of each permit and the issuing agency. Example: USACE Nation Wide Permit 14
• Government Furnished Permit - A permit acquired by NPS or the AE that is provided to the contractor as part of the bid package.
• Contractor Provided Permit - A permit need to conduct a scope of work that a contractor acquires after they win the contract but before work can start. These permits are based on the contractor's means and methods.
• Bid Package - The group of documents that the project team submits to Contracting for approval and then to be published as a Request for Proposals.
•
•
•

## Acronyms
Permit Plan
National Park Service (NPS) - Denver Service Center (DSC) ¦ 8-11-26
Acronyms
AE | Architect/Engineer
CD | Construction Documents
CERCLA | Comprehensive Environmental Response, Compensation, and Liability Act
CFR | Code of Federal Regulations
CO | Contracting Officer
CP | Contractor-Provided
CWA | Clean Water Act
CZMA | Coastal Zone Management Act
DB | Design-Build
DBB | Design-Bid-Build
DD | Design Development
DOI | U.S. Department of the Interior
DSC | Denver Service Center
EO | Executive Order
ESA | Endangered Species Act
ESIA | Energy Independence and Security Act
FAR | Federal Acquisition Regulation
FEMA | Federal Emergency Management Agency
FSF Land | Fee Simple Federal Land
GF | Government-Furnished
IGE | Independent Government Estimate
I-PAF | Initial Permitting Assessment Form
NEPA | National Environmental Policy Act
NEPA DD | National Environmental Policy Act Decision Document
NESHAPS | National Emission Standards for Hazardous Air Pollutants
NFIP | National Flood Insurance Program
NPDES | National Pollutant Discharge Elimination System
NPS | National Park Service
OSHA | Occupational Safety and Health Administration
OSMR&E | Office of Surface Mining Reclamation and Enforcement
PAF | Permitting Assessment form
PD | Predesign
PEPC | Planning, Environment and Public Comment System
PM | Project Manager
PMIS | Project Management Information System
POR | Program of Requirements
PS | Project Specialist
R&HA | Rivers and Harbors Act of 1899
RCRA | Resource Conservation and Recovery Act
RFP | Request for Proposal
SD | Schematic Design
SHPO | State Historic Preservation Office/Officer
SHPO DD | State Historic Preservation Office Decision Document
SMCRA | Surface Mining Control and Reclamation Act
SOS | Scope of Service
US / U.S. | United States
USC | United States Code
USCG | United States Coast Guard
USEPA | U.S. Environmental Protection Agency
USFWS | U.S. Fish and Wildlife Service
USNMFS | U.S. National Marine Fisheries Service
UST | Underground Storage Tank

## Permit Plan
Permit Plan Cover Sheet - Project Data
Project Title: | Usually from PMIS entry
PMIS Number: | XXXXXX | NPS Region: | (Dropdown) | AE Firm Name: | AE Firm Name
PEPC ID Number: | XXXXXX | Park Code: | example: NAMA | AE Contact Name: | AE Staff Name
Funding Source: | Funding Source | Park Contact Name: | Park Staff Name | Date(s) of Assessment: | mm/dd/yyyy, mm/dd/yyyy
DSC PM Name: | DSC Staff Name |  |  | Permits to Contracting No Later Than: | mm/dd/yyyy
DSC PS Name: | DSC Staff Name |  |  | Number of Permit Plans (agreed upon in SD meeting): | XXX
Purpose, Role, Requirements
Complete areas shaded in gray. Acronyms used in this form are defined in the Acronyms worksheet/tab.
The Permit Plan details requirements to aquire a particular permit which is used to schedule, workload, and manage project permits. Permits requiring a permit paln are determined by the AE in the Draft Permitting Road Maps and finalized at the end of the SD meeting.
The AE is required to provide information for and complete this Permit Plan Cover Sheet.
Prepare one permit plan for each permit identified as required during the SD permitting meeting.
Permits | Agency Issuing the Permit | Jurisdiction Federal / States / Local | Notes | Design Provider GF (see FAR GF information) / CP | Estimated Permit Costs from Section 4
Exact Name of Permit 1 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 2 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 3 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 4 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 5 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 6 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 7 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 8 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 9 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Exact Name of Permit 10 | Agency Name | (Dropdown) | Enter short note or use “see note(s) x below” | (Dropdown) | 5000
Notes
Add Notes
Permit 1 - Permit Plan for: | Exact Name of Permit 1
Section 1 - Permit General Information
Permit Standards found at (website): | Standards Name & Link |  | Issuing Agency: | Agency Name
Date of Information: | mm/dd/yyyy |  | Agency Contact Name: | Agency Staff Name
Date of Last Consultation: | mm/dd/yyyy |  | Agency Contact Email Address: | Agency Staff Email Address
Section 2 - Application Requirements - Documents Needed for a Complete Application
Cover Letter from NPS (usally required): | (Dropdown) | Related-Conjoined Permits: | Name Permits
Application Form (typical): | (Dropdown)
Required Supporting Documents (NEPA DD, SHPO DD, reports, drawings, communications, etc.):
1 Document Name |  | 8 Document Name |  | 15 Document Name
2 Document Name |  | 9 Document Name |  | 16 Document Name
3 Document Name |  | 10 Document Name |  | 17 Document Name
4 Document Name |  | 11 Document Name |  | 18 Document Name
5 Document Name |  | 12 Document Name |  | 19 Document Name
6 Document Name |  | 13 Document Name |  | 20 Document Name
7 Document Name |  | 14 Document Name |  | 21 Document Name
Notes: | Add Notes
Section 3 - Permit Acquisition Timeline - Steps in Agency Review Process
Application Preparation Time (typical): |  | Duration (days) | Notes
1 - Review for Completeness: | (Dropdown) | 0 | Add Notes
2 - Analysis of Application: | (Dropdown) | 0 | Add Notes
3 - Step Name: | e.g. Application Meeting | 0 | Add Notes
4 - Public Review: | (Dropdown) | 0 | Add Notes
5 - Step Name: | e.g. Consult with other Agencies | 0 | Add Notes
6 - Step Name: | e.g. Board Meeting | 0 | Add Notes
7 - Administrative Review: | (Dropdown) | 0 | Add Notes
| Total Duration of Agency Review: | 0
Notes: | Add Notes
Section 4 - Permit Acquisition & Costs (Estimate)
| Application Development Cost | Permit Fee | Optional Application Deliverables (with CO approval) | Mitigation Costs | Total
Permit Name | 0 | 0 | 0 | 0 | 0
Notes on Costing Assumptions: | Add Notes
Section 5 - Permit Risk Assessment
Describe Risk in Obtaining this Permit: | Add Description of Risk
Permit 2 - Permit Plan for: | Exact Name of Permit 2
Section 1 - Permit General Information
Permit Standards found at (website): | Standards Name & Link |  | Issuing Agency: | Agency Name
Date of Information: | mm/dd/yyyy |  | Agency Contact Name: | Agency Staff Name
Date of Last Consultation: | mm/dd/yyyy |  | Agency Contact Email Address: | Agency Staff Email Address
Section 2 - Application Requirements - Documents Needed for a Complete Application
Cover Letter from NPS (usally required): | (Dropdown) | Related-Conjoined Permits: | Name Permits
Application Form (typical): | (Dropdown)
Required Supporting Documents (NEPA DD, SHPO DD, reports, drawings, communications, etc.):
1 Document Name |  | 8 Document Name |  | 15 Document Name
2 Document Name |  | 9 Document Name |  | 16 Document Name
3 Document Name |  | 10 Document Name |  | 17 Document Name
4 Document Name |  | 11 Document Name |  | 18 Document Name
5 Document Name |  | 12 Document Name |  | 19 Document Name
6 Document Name |  | 13 Document Name |  | 20 Document Name
7 Document Name |  | 14 Document Name |  | 21 Document Name
Notes: | Add Notes
Section 3 - Permit Acquisition Timeline - Steps in Agency Review Process
Application Preparation Time (typical): |  | Duration (days) | Notes
1 - Review for Completeness: | (Dropdown) | 0 | Add Notes
2 - Analysis of Application: | (Dropdown) | 0 | Add Notes
3 - Step Name: | e.g. Application Meeting | 0 | Add Notes
4 - Public Review: | (Dropdown) | 0 | Add Notes
5 - Step Name: | e.g. Consult with other Agencies | 0 | Add Notes
6 - Step Name: | e.g. Board Meeting | 0 | Add Notes
7 - Administrative Review: | (Dropdown) | 0 | Add Notes
| Total Duration of Agency Review: | 0
Notes: | Add Notes
Section 4 - Permit Acquisition & Costs (Estimate)
| Application Development Cost | Permit Fee | Optional Application Deliverables (with CO approval) | Mitigation Costs | Total
Permit Name | 0 | 0 | 0 | 0 | 0
Notes on Costing Assumptions: | Add Notes
Section 5 - Permit Risk Assessment
Describe Risk in Obtaining this Permit: | Add Description of Risk
Permit 3 - Permit Plan for: | Exact Name of Permit 3
Section 1 - Permit General Information
Permit Standards found at (website): | Standards Name & Link |  | Issuing Agency: | Agency Name
Date of Information: | mm/dd/yyyy |  | Agency Contact Name: | Agency Staff Name
Date of Last Consultation: | mm/dd/yyyy |  | Agency Contact Email Address: | Agency Staff Email Address
Section 2 - Application Requirements - Documents Needed for a Complete Application
Cover Letter from NPS (usally required): | (Dropdown) | Related-Conjoined Permits: | Name Permits
Application Form (typical): | (Dropdown)
Required Supporting Documents (NEPA DD, SHPO DD, reports, drawings, communications, etc.):
1 Document Name |  | 8 Document Name |  | 15 Document Name
2 Document Name |  | 9 Document Name |  | 16 Document Name
3 Document Name |  | 10 Document Name |  | 17 Document Name
4 Document Name |  | 11 Document Name |  | 18 Document Name
5 Document Name |  | 12 Document Name |  | 19 Document Name
6 Document Name |  | 13 Document Name |  | 20 Document Name
7 Document Name |  | 14 Document Name |  | 21 Document Name
Notes: | Add Notes
Section 3 - Permit Acquisition Timeline - Steps in Agency Review Process
Application Preparation Time (typical): |  | Duration (days) | Notes
1 - Review for Completeness: | (Dropdown) | 0 | Add Notes
2 - Analysis of Application: | (Dropdown) | 0 | Add Notes
3 - Step Name: | e.g. Application Meeting | 0 | Add Notes
4 - Public Review: | (Dropdown) | 0 | Add Notes
5 - Step Name: | e.g. Consult with other Agencies | 0 | Add Notes
6 - Step Name: | e.g. Board Meeting | 0 | Add Notes
7 - Administrative Review: | (Dropdown) | 0 | Add Notes
| Total Duration of Agency Review: | 0
Notes: | Add Notes
Section 4 - Permit Acquisition & Costs (Estimate)
| Application Development Cost | Permit Fee | Optional Application Deliverables (with CO approval) | Mitigation Costs | Total
Permit Name | 0 | 0 | 0 | 0 | 0
Notes on Costing Assumptions: | Add Notes
Section 5 - Permit Risk Assessment
Describe Risk in Obtaining this Permit: | Add Description of Risk
Permit 4 - Permit Plan for: | Exact Name of Permit 4
Section 1 - Permit General Information
Permit Standards found at (website): | Standards Name & Link |  | Issuing Agency: | Agency Name
Date of Information: | mm/dd/yyyy |  | Agency Contact Name: | Agency Staff Name
Date of Last Consultation: | mm/dd/yyyy |  | Agency Contact Email Address: | Agency Staff Email Address
Section 2 - Application Requirements - Documents Needed for a Complete Application
Cover Letter from NPS (usally required): | (Dropdown) | Related-Conjoined Permits: | Name Permits
Application Form (typical): | (Dropdown)
Required Supporting Documents (NEPA DD, SHPO DD, reports, drawings, communications, etc.):
1 Document Name |  | 8 Document Name |  | 15 Document Name
2 Document Name |  | 9 Document Name |  | 16 Document Name
3 Document Name |  | 10 Document Name |  | 17 Document Name
4 Document Name |  | 11 Document Name |  | 18 Document Name
5 Document Name |  | 12 Document Name |  | 19 Document Name
6 Document Name |  | 13 Document Name |  | 20 Document Name
7 Document Name |  | 14 Document Name |  | 21 Document Name
Notes: | Add Notes
Section 3 - Permit Acquisition Timeline - Steps in Agency Review Process
Application Preparation Time (typical): |  | Duration (days) | Notes
1 - Review for Completeness: | (Dropdown) | 0 | Add Notes
2 - Analysis of Application: | (Dropdown) | 0 | Add Notes
3 - Step Name: | e.g. Application Meeting | 0 | Add Notes
4 - Public Review: | (Dropdown) | 0 | Add Notes
5 - Step Name: | e.g. Consult with other Agencies | 0 | Add Notes
6 - Step Name: | e.g. Board Meeting | 0 | Add Notes
7 - Administrative Review: | (Dropdown) | 0 | Add Notes
| Total Duration of Agency Review: | 0
Notes: | Add Notes
Section 4 - Permit Acquisition & Costs (Estimate)
| Application Development Cost | Permit Fee | Optional Application Deliverables (with CO approval) | Mitigation Costs | Total
Permit Name | 0 | 0 | 0 | 0 | 0
Notes on Costing Assumptions: | Add Notes
Section 5 - Permit Risk Assessment
Describe Risk in Obtaining this Permit: | Add Description of Risk

## Data (hidden)
Dropdown 1
(Dropdown)
Region 1 - North Atlantic
Region 2 - South Atlantic
Region 3 - Great Lakes
Region 4 - Mississippi Basin
Region 5 - Missouri Basin
Region 6 - Arkansas, Rio Grande, Texas, Gulf
Region 7 - Upper Colorado Basin
Region 8 - Lower Colorado Basin
Region 9 - Columbia, Pacific Northwest
Region 10 - California, Great Basin
Region 11 - Alaska
Region 12 - Pacific Islands
Dropdown 2
(Dropdown)
Federal
States
Local
Dropdown 3
(Dropdown)
Government-Furnished (GF)
Contractor-Provided (CP)
Dropdown 4
(Dropdown)
Yes
No