## SAMPLE
Project Meta Data
PROJECT TITLE: Tamiami Trail Modifications: Next Steps - 2.6 Mile Bridge Project | [6 empty] | PMIS #: | EVER 196127
PARK: Everglades National Park |  |  | Permitting Lead: HDR | PROGRAM: LIC |  |  | PEPC ID#: | 26159
1st PARK CONTACT: Dave Sikkema |  |  | 2nd PARK CONTACT: | REGION: | South East Region
DSC PM: Lydia Creager, PE |  |  | DSC PS: | Assessor's Name: Chip M.
A/E: HDR Engineering, Inc. |  |  | A/E CONTACT: Daniel Ford, PE | Dates of Assessment - |  | First: June 2013 | Most recent: 11/13/13
Notes:
Jurisdictional Assessment
Questions Examining Jurisdiction - Who needs to be involved?
Is the site COMPLETELY on NPS land? |  |  |  | No | Project includes part of USACE canal
What is the classification of the jurisdiction for the Park at the site? See RM39-1, pg. 9. 1 |  |  |  | Unknown
Has the site's jurisdiction been DOCUMENTED? |  |  |  | Yes | FDOT and NPS jurisdiction is clearly defined.
Questions regarding circumstances that might give an agency jurisdiction at a site.
Is there standing water on site? |  |  |  | Yes | Project will occur within inundated marsh systems of Everglades National Park.
Are there water channels on site? |  |  |  | Yes | The L-29 Canal will be part of this project. In addition, open water channels occur at each cross-drain culvert under Tamiami Trail.
Is there any know local jurisdiction on the site? |  |  |  | No | Miami-Dade County has expressed a desire to exercise jurisdiction over the project at the NPS' discretion. NPS has indicated the County will not be included in permitting process.
Have the site's structures been reviewed? (levees, utilities, etc.)? |  |  |  | Unknown | Needs further review in preliminary design phase.
Other designations that may carry rights (special waters, critical habitat, easements etc.)? |  |  |  | Yes | Everglades classified as an "Outstanding Florida Water" (OFW).
List other existing permits that include the site: Not Applicable. The FDEP permit for the recently completed 1-mile bridge project was not formally issued by FDEP. The 1-mile bridge project included "road strengthen" for the entire 10+ mile Tamiami Trail and permit conditions for that aspect of the project would have included the project limits for the proposed 2.6-mile bridge. As such, there are no existing permits affecting this project.
Notes on Jurisdictional Assessment: Environmental Scientists with HDR Engineering, Inc. established the landward extent of state waters as defined in Chapter 62-340 FAC as ratified in Section 373.4211 FS, and the extent of U.S. waters as defined in the Regional Supplement to the Corps of Engineers Wetland Delineation Manual: Atlantic and Gulf Coastal Plain Region (Version 2.0). Wetland and Surface Water jurisdictional limits were established on both the north (L-29 Canal) side and south side (Everglades wetlands) of Tamiami Trail. In preparation for the GPS data collection, the limits of each survey area were uploaded to a handheld Trimble GeoXT GPS unit as a field guide and a GIS layer created to map wetland and surface water jurisdictional limits was configured to allow post-processing in the office to ensure sub-meter accuracy of the captured points.
Resource Topics - Compliance Related
Not part of project |  | Listed Species Incidental Take: Fish (NPS typically avoids incidental take)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: |  | ESA § 95,7 | Not Applicable
No | State:
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision:
Part of project |  | Listed Species Incidental Take: Marine Mammals (NPS typically avoids incidental take)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USFWS | ESA § 95,7, MMPA6 | Not Applicable |  | Contractor to follow Standard Manatee Construction Conditions for In-Water Work 2011
No | State: | FFWCC | Florida Manatee Sanctuary Act; Chapter 379.2431(2) Florida Statutes | Not Applicable |  | Contractor to follow Standard Manatee Construction Conditions for In-Water Work 2011
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision:
Part of project |  | Listed Species Incidental Take: Terrestrial (NPS typically avoids incidental take)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USFWS | ESA § 95,7, MBTA8 | Not Applicable |  | Selected contractor will be required to follow Standard Protection Measures for the Eastern Indigo Snake (USFWS 2013) during construction.
No | State: | FFWCC | Chapter 379 Florida Statutes | Not Applicable |  | Selected contractor will be required to follow Standard Protection Measures for the Eastern Indigo Snake (USFWS 2013) during construction.
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision:
Part of project |  | Protected/Critical Habitat (NPS typically avoids incidental take)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USFWS | ESA § 95,7 | Not Applicable |  | Entire project within wood stork Core Foraging Area. Proposed wetland impacts may require mitigation to replace lost foraging habitat.
No | State: | FFWCC |  | Not Applicable |  | Entire project within Florida panther Primary Protection Zone.
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision: CDE-2013.11.12: No wood stork rookeries or panther habitat?
Part of project |  | Waters of the US and Wetlands (or other Special Aquatic Sites)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Yes | Federal: | USACE, USEPA | CWA § 40410, EO 119909, | Section 404 D&F |  | Permit application submittal by NPS/HDR. Review, approval and issuance by USACE.
Yes | State: | FDEP | Chapter 62-340 FAC | CERPRA Permit |  | Permit application submittal by NPS/HDR. Review, approval and issuance by FDEP.
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision:
Unknown |  | Floodplain (Construction in)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | FEMA | 44 CFR12, EO 1198813, | NFIP Permit
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Coastal Lands - Usually addressed in NEPA on NPS land. If project is NOT on NPS land review this topic.
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | NOAA | CZMA14,
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Navigable Waters
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USACE, USCG | R&HA 1899 §§9-1011
No | State:
No | Local:
Basis of Decision:
Part of project |  | Water Quality Certification (required if project has federal permit)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Yes | Federal: | USACE | CWA § 40410, EO 119909, | Section 404 D&F |  | Federal Water Quality Certification requirement satisfied by issuance of CERPRA Permit by FDEP
Yes | State: |  | Chapter 62-340 FAC | CERPRA Permit
No | Local:
Basis of Decision:
Not part of project |  | Mine Land
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | DOI-OSM | SMCRA
No | State:
No | Local: | ---- | ---- | ---- |  | Local jurisdiction typically does not apply to NPS for this topic
Basis of Decision:
Not part of project |  | Zoning - Not normally required on NPS land
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | OTHER TOPIC:
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Design Topics - Integrated into Plans
Not part of project |  | Septic System
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Wastewater Collection System
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Wastewater Pump/Lift Station
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Wastewater Treatment Plant
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Pretreatment, i.e. Oil/Water Separator
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Part of project |  | Stormwater Management (permanent)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Yes | Federal: | USACE | Section 404 & CWA | Section 404 D&F |  | USACE requires WQC before Section 404 issuance.
Yes | State: | FDEP | Chapter 62-330 FAC | CERPRA Permit |  | Issuance of CERPRA Permit certifies WQC.
No | Local:
Basis of Decision:
Not part of project |  | Aggregation Pt. or Transfer Facility
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Landfill
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: |  | RCRA, 36 CFR Part 6 §6.52, NPS Guidance3,
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Drinking Water Treatment Plant
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Well Construction (includes geothermal)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Underground Injection
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Tank Construction (AST or UST)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USEPA | US Code, Title 42, Chap 82, Sub chap IX | Permit
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Hazardous Material/Waste Storage
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USEPA | RCRA , OSHA, and NESHAPS | Permit
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Communication Tower
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | FCC4 |  | Permit
No | State:
No | Local:
Basis of Decision:
Part of project |  | Roadway/Highway and Associated structures
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
Unknown | State: | FDOT | FDOT Standard Specifications for Road and Bridge Construction 2014 | Unknown |  | All roadway, bridge and drainage aspects of the project must conform with FDOT Standard Specifications.
No | Local:
Basis of Decision: Permit type, if any, unknown at this time pending further coordination with FDOT.
Unknown |  | OTHER TOPIC: Utility relocations, both temporary and permanent, must be considered in design phase.
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Construction Topics
Not part of project |  | Construction Air Pollution - Usually handled via Division 1 Specifications
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal: | USEPA | Clean Air Act-Title II
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Airport Hazard/Safety Clearances
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Railroad Crossing
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Unknown |  | Highway Encroachment Permit
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
Unknown | State: | FDOT | FDOT Standard Specifications for Road and Bridge Construction 2014 | Driveway Connection Permit
No | Local:
Basis of Decision: Need to coordinate with FDOT to identify if Driveway Connection Permits will be required for access ramps from the proposed bridge to Everglades Safari and Lincoln Financial Radio Tower site.
Part of project |  | Traffic Control
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
Yes | State: | FDOT | FDOT Standard Specifications for Road and Bridge Construction 2014 | Approved MOT Plan |  | Maintenance of Traffic (MOT) plan will be required during construction.
No | Local:
Basis of Decision:
Not part of project |  | Digging / Excavation Permit - Usually handled via Division 1 Specifications
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Noise Abatement - Usually handled via Division 1 Specifications
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Part of project |  | NPDES over an acre Construction Permit
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Yes | Federal: | USEPA | CWA-Section 401 | Not Applicable
Yes | State: | FDEP | Section 403.0885 F.S. and 62-621.300(4), F.A.C. | NPDES Stormwater Permit |  | Future contractor to secure NPDES permit.
No | Local:
Basis of Decision:
Part of project |  | Temporary Utilities (Communication, Electrical, Water, Sanitary Sewer, etc.)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Hazardous Waste Removal, Transportation, and disposal
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Unknown |  | OTHER TOPIC:
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Operational Permits - Owner
Not part of project |  | AST Operation
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | USEPA | Clean Air Act Title V, NESHAP | Permit
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | UST Operating
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | USEPA | Clean Air Act Title V | Permit
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Stationary Source Air Quality
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Solid Waste Incineration Unit
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Septic System
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Wastewater Treatment Plant
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Pretreatment (e.g. Oil/Water Separator)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Wastewater Pump Station
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Food Services (usually acquired by the Concessioner)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Drinking Water Treatment Plant
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | USEPA | Safe Drinking Water Act | PWS permit
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Well Construction (includes geothermal)
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Underground Injection Well
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Waste Transfer - Aggregation Facility
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Landfill
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Small Quality Generator
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
No | Federal:
No | State:
No | Local:
Basis of Decision:
Not part of project |  | Hazardous Material/Waste Storage
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | USEPA | RCRA-40 CFR Parts 264 and 270
Unknown | State:
Unknown | Local:
Basis of Decision:
Not part of project |  | Communication Tower
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal: | FCC4 |  | Permit
Unknown | State:
Unknown | Local:
Basis of Decision:
Un-Reviewed |  | OTHER TOPIC:
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision:
Un-Reviewed |  | OTHER TOPIC:
Needed? | Jurisdiction: | Agency | Law, regulation, etc. | Permit Type: |  | Requirements, Actions, Etc.:
Unknown | Federal:
Unknown | State:
Unknown | Local:
Basis of Decision: