Permitting Road Map

National Park Service (NPS) - Denver Service Center (DSC) | 8-11-26

# Project Information

Date:	mm/dd/yyyy	Park Code:	example: NAMA	Project Management Information System (PMIS) Number:	XXXXXXX

To:	Names of DSC Project Manager and DSC Contracting Officer	From:	Project Manager, Firm Lead and/or Permit Lead, Firm Name

Project Name:	(Official Name in PMIS)

# Instructions

The Permitting Road Map outlines the requirements of each permit identified in the Permitting Assessment Form (PAF) and transitions the DSC Project Permitting Process (PPMP) from Scoping to begin Planning.

Architect/Engineer (AE) Requirements

- Outline each permit's requirements throughout design, construction, closeout, and operational phases.

- Recommend which permits should be acquired during design or construction.

- Recommend if a full Permit Plan is required. Discussed during end of Schematic Design (SD) permitting meeting. Typically, permits acquired during design require a Permit Plan.

| Permit (Exact name of permit) | Agency Issuing Permit (Name of Agency & Branch) | Jurisdiction (Federal / States / Local Name) | Notes (Number(s) from Notes section below) | Acquisition (Design or Construction or Operation) | Permit Plan Required (Yes / No)) | Design Phase Requirements | Construction Phase Requirements | Closeout Requirements | Operational Requirements |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Add Rows as Needed |  |  |  |  |  |  |  |  |  |
| Example Permits Below |  |  |  |  |  |  |  |  |  |
| Example: CWA (Clean Water Act) §404 -Nation Wide Permit (NWP), #3 (Maintenance) | USACE (US Army Corps of Engineers), Sacramento District | Federal | 1-2 | Design | Yes | Predesign meeting, permit documentation development, application assembly (including a Compensatory Mitigation Plan), application submittal, 90-day USACE review, permit issued, permit review acceptance & signed, final integration into Request for Proposal (RFP). | Implementation of permit provisions (project start and conclusion notification) | NWP has general requirements that include closure, transfer of Compensatory Mitigation Plan to Park | Park executes Compensatory Mitigation Plan |
| Example: CWA §402 - NPDES (National Pollutant Discharge Elimination System) Construction General Permit (aka SWPPP (Stormwater Pollution Prevention Plan)) | CA RWQCB (California Regional Water Quality Control Boards), Fresno Office | Federal, administered by state | 3 | Construction | No | Review current standards, develop required sheets, included in Division 1 Specifications (015723), note not needed for closure in Division 1 Specifications (017700-1.5). | Prepare SWPPP, File NOI, conduct during construction monitoring, and follow provisions | File Notice of Termination (NoT) | None |

Notes:

- Example: NWP 3 – First 30-days of review period is for determination of application completeness. If the application is found incomplete, then the 30-day period can be paused or reset.

- Example: NWP 3 – The Mitigation Plan is required due the area (0.2 acres) of the impacts. The preparation of the Mitigation Plan should be a separate task / sub-task and will need to involve Compliance.

- Example: SWPPP – Because of the way California administrators the SWPPP, it will be important to identify the LEVEL during design and include the requirements into the SOS (Scope of Services) / sheets / specifications.