| Negotiated Rulemaking (NR) Advisory Committee Process | NEPA Process |
| --- | --- |
|  | June 3, 2005 Draft ISR posted on PEPC for internal review |
|  | August 5, 2005 Review/Finalize ISR (contractor has 10 days after receipt of NPS comments to finalize) Draft EIS NOI prepared |
|  | December 2005 IDT meets to define criteria, thresholds, data, etc. (decision criteria – i.e. how you are going to objectively set up criteria to open or close areas to dogs, T & E species, conflict over uses, etc.) Socioeconomic site visit and data gathering. |
| February 17, 2006 Notice of Establishment for Committee and Notice of Committee Meeting published in Federal Register; Members appointed | February 22, 2006 EIS Notice of Intent published in Federal Register; Starts 60 day scoping (ends April 2006). Contractor begins analyses of no action alternative (existing management continued) |
| March 6, 2006 NR Committee Meeting #1: Introductions of DFO/Committee, Facilitator Evaluation, Protocols, Applicable Statutes/Regulations, NEPA Process/Schedule, NPS Sideboards, Public comment. | March 2006 Information collection continues |
| April 4 and 5, 2006 Attend NEPA Public Scoping workshops. Provide comments to NPS-NEP A public scoping (comment period ends 4/24). | April 4 and 5, 2006 Public scoping workshops |
| April 18, 2006 NR Committee Meeting #2: Information Updates [Accelerated Resource Protection Rulemaking], Revise Draft Protocols, , Committee Schedule/Logistics, Public comment. | April Content Analysis of Public Scoping Comment Development of No Action Alternative And final impact thresholds; data gap Analysis complete |
| May 15, 2006 NR Committee Meeting #3: Final Protocol revisions approval, NPS Parameters (Sideboards) and NEPA EIS No Action Alternative, Draft Collaborative Approach to Decision Making, Information Needs (including creation of a Technical Subcommittee and initial charge), Public comment. | May 2006 Complete preliminary analysis of No action alternative |
| June 2006: Date TBD Technical Subcommittee Meeting #1: Identify essential data, review available data/data by geographic areas and identify data gaps, develop recommendation for Committee, Next steps to prepare for Committee mtg. (Possible Committee field trip/s or individual visits to dog walking locations with GGNRA) |  |
| June 22, 2006 NR Committee Meeting #4: Review data needs recommendation from Technical Subcommittee Meeting #1 and decide next steps, Review initial Key Interests and Issues Table, Discuss potential evaluation criteria, Public Comment. Option: Present draft internal scoping report prepared for concurrent NEPA process. | June 2006 Public scoping content analysis complete and posted on PEPC. Review and revision of no action impact analysis |
| July 2006 Technical Subcommittee Meeting #2: Further discussion of data needs based on NR Committee Mtg#4. Include assessment of NEPA database for the various locations discussed during Committee #4. Option: Caucuses to refine Key Interests and Issues Table. Option: Develop initial options for GGNRA-wide issues such as voice control criteria. August 2006 NR Committee Meeting #5: Discuss outcomes of Technical Subcommittee Meeting #2; Review revisions to Key Interests and Issues Table; Review initial options for GGNRA-wide and individual sites and evaluate; Focus on options for GGNRA-wide issues; Agree on next steps. | July 2006 IDT meeting: Desired Future Conditions For each site, resource based, visitor Experience, constraints; preliminary Alternatives development August Continued refinement of above |
| September 2006 Subcommittee meetings: TBD Caucus efforts: TBD | September 2006 Alternatives Development continues, concurrently with Impact analysis |
| Early October 2006 NR Committee Meeting #6: Focus on GGNRA area-specific dog management options, and review draft rule language pertaining to GGNRA-wide dog management options | Late October 2006 Chapter 4 drafted (Impact Analyses of Alternatives), Economic analyses of alternatives completed (draft report) |
| Early November 2006 NR Committee Meeting #7: Review draft rule language related to area-specific options; discuss integration of GGNRA-wide and area-specific options, and rule language addressing options/agreements discussed; discuss options for dealing with topics/areas where consensus has not yet been reached |  |
| Early December 2006 Subcommittee or caucus meetings to resolve any outstanding issues Public Outreach/Implementation Subcommittee Meeting | December 2006 Incorporate NR Committee findings into EIS alternatives Begin Impact analysis per NEPA |
| January 2007 NR Committee Meeting #8: Finalize rule language on areas of agreement and, if needed, options for addressing topics/areas where consensus has not yet been reached |  |
| TBD Potential Committee meeting to discuss any implications of the NEPA process to the agreements reached by the Committee | 2007 DEIS out to Public for Review (would contain findings of NR Committee). This would be released about the same time as the Proposed Rule for Dog Management at GGNRA for public comment. |
|  | 2008 FEIS and Final Rule complete, with a Record of Decision. |