## Intro and Definitions
| CC-ZION003-25 | Appendix D: Deferred Maintenance Work Order List
The Concessioner must cure, within the first two years of the Contract’s term, all deferred maintenance (DM) and legislatively mandated work (LM) for Concession Facilities, called collectively simply deferred maintenance or DM. In the first year of the Draft Contract, the Service will work with the Concessioner to develop a prioritized and comprehensive list of task orders, developed from the list provided here. Below is a point-in-time list of work orders which the Service believes properly represents the DM and LM that will need to be cured at the start of the Contract. Conditions and quantities may vary from the descriptions and quantities provided herein.
Definitions of Work Subtypes Acronyms
Acronym | Asset Management Term | NPS Definition
DM | Deferred Maintenance | Maintenance that was not timely or properly conducted. Continued Deferred Maintenance will result in Deficiencies.
CRDM | Component Renewal Deferred Maintenance | Component Renewal work that was not performed when it was scheduled or should have been performed based on wear. The maintenance is, therefore, past due and delayed. Continued deferment of maintenance will result in Deficiencies
LMAC | Legislatively Mandated Accessibility | Faults or defects in an existing system/asset/equipment that must be corrected in response to accessibility legislation.
LMCO | Legislatively Mandated Code Compliance | Faults or defects in an existing system/asset/equipment that must be corrected in response to code requirements
LMFS | Legislatively Mandated Fire Structure | Faults or defects in an existing system/asset/equipment that must be corrected in response to structural fire regulatory or code requirements.
LMLS | Legislatively Mandated Life Safety | Faults or defects in an existing system/Component/equipment that must be corrected in response to life and safety regulatory or code requirements
RMDM | Recurring Maintenance Deferred Maintenance | Recurring Maintenance that was not performed when it was scheduled or should have been performed based on wear. The maintenance is, therefore, past due and delayed. Continued deferment of maintenance will result in Deficiencies.

## DM and LM ZION003-25
Deferred Maintenance Work Order List (CC-ZION003-25)
ASSET CODE | ASSET DESCRIPTION | WORK SUBTYPE | WORK ORDER DESCRIPTION | PRIORITY YEAR
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 24"x22" Porcelain, Lavatory, Drop-in-Counter Top, Located in the storage room on the southwest corner on the second floor. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 10"x10" Chrome Finish, Faucet - Lever Style, Located in the vanity in the storage closet on the second floor in the southwest corner. Faucet also includes spray wand. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 41"x24" Self-Contained, through the wall, Package Unit - PTAC, General Electric brand. Located in rooms: 213, 211, 212, 210, 208, 207, 205, 206, 204, 201, 203 and located in room 209 bedroom suite. Also located in room 212 bedroom suite. Also located in the accessible bedroom number 101 on the main level. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 41"x24" Self-Contained, through the wall, Package Unit - PTAC, Original PTAC unit. Located in rooms 202 and accessible bedroom 103. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 48"x8" Wall Heater, Electric Wall Heater, Located in the linen storage closet on the second floor in the southeast corner. Located on the east wall in the mechanical room on the southeast corner of the building. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 30"x8" Wall Heater, Electric Wall Heater, Located in the fire riser room in the crawlspace along the east wall. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 5"x10" Single Bulb, Exterior Light Fixture, Located on the exterior walls above each guest room door with patio access. | 2025
65758 | ZILO B225 Motel A-Sentinel | CRDM | Replace at end of useful life. 2"x6" Wood Planking for, Deck Flooring Material, Painted, Redwood, 2364 SF Located at all decks | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Adjust Security Latches to be between 34" and 48" above the floor as per Department of Justice, ADAABAG 404.2.7, 309.4 on Guest Rooms 101-104. 36" X 80", Solid Core - Wood, Fire Door, Self Closer, Key Card Entry Access, Stained, With (1x4) beveled transition strip 36” 2” hollow metal frame , | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Replace threshold with one that is a maximum of 1/2" at accessible doors and beveled with a slope no greater than 1:2. As per ADAABAG Section 404.2.5. 36" X 80", Solid Core - Wood, Fire Door, Self Closer, Key Card Entry Access, Stained, With (1x4) beveled transition strip 36” 2” hollow metal frame , Located in guest rooms 101, 102, 103, and 104 | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Adjust Door closer to sweep period of the closer adjusted so that from an open position of 90 degrees, the door will take at least 5 seconds to move to a point 12 degrees from the latch. As per ADAABAG Section 404.2.8.1. 36" X 80", Solid Core - Wood, Fire Door, Self Closer, Key Card Entry Access, Stained, With (1x4) beveled transition strip 36” 2” hollow metal frame , Located in guest rooms 101, 102, 103, and 104 | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Adjust Closet Shelf and Rod to be between 34" and 48" above the floor per Department of Justice, ADAABAG. 37" X 1" X 18", Wood, Shelving, With 1” diameter rod. Located in guest room 103 and 104. | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Add a horizontal grab bar at the foot of the tub (by the controls) that is at least 24" long for stabilization as per Department of Justice, ADAABAG 607.4.1.2. Stainless Steel, Grab Bar, (5) 24” (1) 48”, Located in Guest room 101, 102, 103, 104. | 2025
65758 | ZILO B225 Motel A-Sentinel | LMAC | Adjust water flow so that it is at least 4" high as per ADAABAG Section 602.6; Stainless Steel, Drinking Fountain, Single Basin, Located on the main floor in the center of the building on the west side wall. | 2025
65758 | ZILO B225 Motel A-Sentinel | LMCO | Label Electrical panel as per the NEC Code Reference 110.22, 20"x44" Metal Panel Box, Electrical Sub Panel, Siemens/ITE brand, with, 54 breaker 250 amp, Located in the east wall in the mechanical closet on the main floor in the southeast corner of the building (Panel E) | 2025
65758 | ZILO B225 Motel A-Sentinel | LMFS | Add emergency lighting two on the first floor and two on the second floor; Wall Mounted, Emergency Lighting | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Replace at end of useful life. 4", Carpet, Baseboard Trim, 46 LF, Located in storage second floor west end | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Remove any loose or deteriorating finish, sand trim surface lightly, caulk joints and cracks, patch minor damage, then replace with new finish coat. 1"x2" Wood, Door & Window Trim, Stained, 51 LF Located in storage closet second floor west end | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Remove any loose or deteriorating finish, sand trim surface lightly, patch minor damage then replace with new finish coat. 1"x3" Wood, Wall Trim, Stained, 5 LF each, 115 LF total Located on half walls in vanity area throughout building | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in storage south side first floor | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in storage closet first floor north end | 2025
65758 | ZILO B225 Motel A-Sentinel | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in linen closet first floor south side | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 12"x14" Ridged Ducting for, Air Distribution Ductwork - Supply & Return, A/C duct located in the attic area only in the center of the building. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. Shut-off Valves, Located throughout in all guest rooms. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 2" Diameter Galvanized, Hot & Cold Water, Supply Piping, Waste piping throughout the building. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. Galvanized, Hot & Cold Water, Supply Piping, 1/2" Diameter, Water supply located throughout the building | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 4" Diameter Galvanized, Hot & Cold Water, Supply Piping, Waste pipes throughout the building. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 1" Diameter Galvanized, Hot & Cold Water, Supply Piping, Water supply lines located throughout the building | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. Metal, Floor Drain, 4 inch diameter opening, 2 inch piping, Located in the crawlspace in the fire riser room. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 41"x24" Self-Contained, through the wall, Package Unit - PTAC, Original PTAC unit. Located in rooms: 135, 133, 130, 233. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 41"x24" Self-Contained, through the wall, Package Unit - PTAC, Located in rooms: 229, 231, 131, 115, 127, 128, 136, 138, 140, 227, 223, 220, 117, 119, 122, 123, 125, 129, 132, 118, 216, 217, 221, 228, 238, 240, 242, 232, 116. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 60"x7" Wall Mounted, Electric Baseboard Heater, Located in the housekeeping office on the south wall. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 32"x8" Wall Mounted, Electric Baseboard Heater, Located in the maintenance room in the northeast corner on the main floor on the east wall. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 30"x8" Wall Mounted, Electric Baseboard Heater, Located in the maintenance closet off the main corridor in the northeast corner on the east wall. Also located in the fire riser room in the crawlspace along the west wall. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 6"x3" Manual controlled, Thermostat, Located in the center of the building on the east wall. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 4" Diameter, Dual Hook-up, Exterior Standpipe Connection, Located on the east side of the building in the northeast corner outside the maintenance room closet. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 6"x9" Metal Panel Box, Service Disconnect, Single Arm, Square D brand, with, 125 Amp/3 Wire System, Located in the fire riser room in the crawlspace along the west wall. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 10"x10" Ceiling Mounted, Emergency Lighting, Located on the north side of the building near the east entrance outside room 236 on the corner of the building. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 10"x10" Metal, Electrical Junction Box, Located in the fire riser room in the crawlspace along the east side of the wall. Metal junction boxes serve the fire riser system. | 2025
65759 | ZILO B226 Motel B-Watchman | CRDM | Replace at end of useful life. 12"x7" Metal, Electrical Junction Box, Located in the fire riser room in the crawlspace along the east side of the wall. Metal junction boxes serve the fire riser system. | 2025
65759 | ZILO B226 Motel B-Watchman | DM | Re-Attach Fallen and Missing Insulation located in various areas through the crawlspace to maintain proper thermal and energy barrier as designed. (284 SF) | 2025
65759 | ZILO B226 Motel B-Watchman | DM | Connect Bathroom Vent Pipes at various location around the attic, to prevent moisture buildup from occurring. | 2025
65759 | ZILO B226 Motel B-Watchman | LMCO | Replace the hard gas line with flex gas piping as per IBC Ref. Code (413.4.1) Gas Fired, Water Heater - Commercial, Bradford White, 100 Gallon, Located in north corner of the mechanical room. | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Rubber, Baseboard Trim, 253 Located in linen closet, west end, second floor and laundry room, first floor, west end | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. 4", Carpet, Baseboard Trim, Located in maintenance office | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Rubber, Baseboard Trim, 22.5LF Located in east exterior mechanical room | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in linen closet east end, second floor | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in linen closet, east end, first floor | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in housekeeping office | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in office second floor west end | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, With metal transition 11”x27”, Located in second floor storage west end | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in east exterior mechanical room | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in exterior mechanical room west side | 2025
65759 | ZILO B226 Motel B-Watchman | RMDM | Remove damaged wallpaper and replace with like patterned covering. Drywall, Interior Wall Covering Material, Wallpaper, 8 Ft. high, 181 LF Located in linen closet, west end, second floor, and linen closet, east end, first floor and maintenance closet first and second floor east end | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Single-Ply EPDM, Roof Finish, Rubberized, Located at deck surface of front deck and small roofs to left and right over lobby corners. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 24"x48" , Floor Drain, Floor drain. Located with abandoned grease trap near the ice machine. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 24" Diameter Metal, Kitchen Exhaust Hood/Fan, Located on the gable end of the roof that is located above the dining room. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Electrical Junction Box, Located on the ceiling of storage room 128 near the north, next to the door. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 32" X 80", Wood, Exterior Entrance Door, Lockset with Key, Painted, Located at fire riser shed | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 6"x8" Chrome Finish, Faucet - Dual Handle, Located with the server sink in the kitchen near the south entrance from the dining room to the kitchen. Also located near the cased opening separates the kitchen from the EDR. Also located with the service sink in the coffee bar. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 8"x6" Chrome Finish, Faucet - Single Valve, Knob style. Located with the service sink on the east wall of room 201D. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Chrome Finish, Faucet - Lever Style, Located in restrooms 212 and 213 off the EDR. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Stainless Steel, Drinking Fountain, Single Basin, Located in the main lobby next to the men’s and women’s restrooms. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Gas Fired, Forced Air Furnace, Luxair heating and cooling unit. Located along the south wall of storage room 126 in the basement. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Ares model air handling unit, with 41" x 39" vent with filter. Model number: MHMua3-1b-18. Located on the northern half of the roof inside the enclosure. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 48"x30" Metal, Cold Air Return Grill, Located in the dining room above the door that goes to the back kitchen and EDR area next to the bartending station. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 16"x16" Metal, Supply Register, Located on the north wall in the northeast corner of the lobby outside the women’s restroom. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 27"x22" Metal, Supply Register, Located on the east wall in the northeast corner of the lobby on the main floor just outside the women’s restroom. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 24"x8" Wall Heater, Electric Wall Heater, Located in the fire riser room along the north wall next to the door. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 6"x4" Manual controlled, Thermostat, Located in the northeast corner of the main lobby area outside the women’s restroom, next to the door that leads to the bus offices. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Metal Panel Box, Service Disconnect, Single Breaker, With two single arm 15 Amp breakers, with two 20 Amp breakers, with two 30 Amp breakers. Located in the fire riser room in the southwest corner. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 36"x90" Metal Panel Box, Main Electrical Service Panel, Siemens/ITE brand, with, Main service disconnect with one 1000 Amp breaker, one 100 Amp breaker, three 300 Amp breakers, one 400 Amp breaker, two 150 Amp breaker, with attached 24" x 24" metal box. Located in the northeast corner of the exterior behind the mechanical closet off the kitchen café area. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. 9"x6" , Interior Light Fixture, With chrome finished fixture, with grilled. Includes on/off switch and one outlet. Located on the stairs from the main floor to the upper dining room. | 2025
65760 | ZILO B224 Main Zion Lodge | CRDM | Replace at end of useful life. Wall Mounted, Emergency Lighting, Located above the elevator in the dining room on the upper floor. Also located along the west wall of 201E. One located in the auditorium in southwest corner of the room. One located in the bus office area that is located behind the front lobby. One located in the room in the gift shop area just outside the gift shop office on the south wall. Also located in the café area along the south wall. One locating the café kitchen area along the east wall on the north east corner. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace Rotted Wood Beams at front of porch caused from water damage. The beam ends soft and weak at the vertical connections of the columns. Recommend replacement of affected wood beam members. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace Damaged Siding at base of wall against kitchen wall at EDR driveway has suffered sever water damage and requires replacement. 1"x12" Wood, Exterior Wall Trim, Painted, 154 LF Located at building corners | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace rotting trim at porch perimeter. 1"x8" Wood, Exterior Wall Trim, Painted, 181 LF Located as belly board where building height exceeds 1 story, and at gable ends at ceiling line. Located at edge of porch as rim board. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace cap at rear of structure is rusted away in many locations, creating vulnerability to further water damage. Replace Damaged sections. 6"x2" Aluminum, Exterior Wall Trim, Painted, Cap flashing for stone masonry, 184 LF Located about base where stone and wood siding meet save at facade at lobby, gift shop, and cafe. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace approximately 25% of shingles at ridge seams, and 10% of shingles overall, due to damage. Cedar Shingle, Roof Finish, Painted, Located in various locations on the main structure roofs, fire riser roof, and west storage roof. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Unclog and repair gutters at front of the porch. Currently clogged and leaking, causing damage to columns and support beams. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Repair leaking pipe at gauge and at shut-off valve located in the storage room (126) 1/2" Diameter Galvanized, Hot & Cold Water, Supply | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Repair leaking waste pipe located in the storage room (128) that is being held together with duct tape. and the pipe coming down from the kitchen drain that is leaking. 4" Diameter Plastic - ABS , Waste & Vent Piping, Main waste line. | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace Missing fan blades on fans located in Auditorium 16" Diameter 5-Blade, Ceiling Fan, with 3 lights, Dropped down from ceiling 24". | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Replace Damaged Handrail along sidewalk to EDR east entrance is damaged for approximately 50% of its length (approx. 37 feet). | 2025
65760 | ZILO B224 Main Zion Lodge | DM | Remove Dirt Around Post Bases that is piled about the wood bases of the deck support posts, leading to possible damage. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Change Door Threshold Height on the lobby entrance doors have rises of more than 1/2." Change threshold height to meet ADAABAG standards.36" X 84", Metal, Exterior Entrance Door, with Panic Hardware, Deadbolt and Door Handle, Factory Finish, With 26x68 vision lite, Located at east, west, and central lobby entrances as well as west cafe entry | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Adjust Door Hinge for ease the maximum force to open to 5 pounds of less as per ADAABAG Section 309.4. 36" X 80", Solid Core - Wood, Specialty Door, Self Closer, Stained, Wood frame, Located at men’s and women’s bathroom | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Adjust Door for easy to open with 5 pounds of maximum force as per ADAABAG Section 309.4. Located in men's and women's EDR Restrooms. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Replace threshold with one that is a maximum of 1/2" at accessible doors and beveled with a slope no greater than 1:2. As per ADAABAG Section 404.2.5. 36" X 80", Solid Core - Wood, Fire Door, Self Closer, Key Card Entry Access, Stained, With (1x4) beveled | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Replace door lockset with one that is easy to grasp with one hand and does not require tight grasping, tight pinching or twisting of the wrist to operate, 36" X 78", Solid Core - Wood, Specialty Door, Stained, Single panel, wood frame, Located at front desk office | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Install minimum of 24" Grab bar positioned from centerline of the toilet on the open side as per ADAABAG Section 604.5.2. Location in the 5" accessible stall in Women's Restroom | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Install minimum of 24" Grab bar positioned from centerline of the toilet on the open side as per ADAABAG Section 604.5.2. Location in the 5" accessible stall in Men's Restroom | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Add a self closing door to the 5' accessible restroom stall doors as per ADAABAG Section 604.8.1.2. Located in women’s bathroom | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Raise the grab bars to be located between 33" and 36" from the floor surface or ground surface as per ADAABAG Section 609.4. Located in both Men's and Women's EDR Restrooms | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Install rear grab bar positioned a minimum of 12" to the centerline of the toilet as per ADAABAG Section 604.5.2. Located in both Men's and Women's EDR restrooms. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Replace non-compliant handrail with rail of a diameter 1-1/4" to 1-1/2" as per ADAABAG Section 505.7.1. 505.7.2. Located lobby to dining room. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Extend handrails at least 12" plus one tread width beyond the bottom riser as per ADAABAG Section 505.10.3. Located in the lobby to dinning room. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Add a self closing door to the 5' accessible restroom stall doors as per ADAABAG Section 604.8.1.2. Located in men’s bathroom | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Adjust elevator door so that the door will remain open for at least 20 seconds as per ADABAG Section 407.3.3.3; Passenger Elevator, Montgomery elevator. Passenger/hydraulic elevator. Two stops with open/close fire alarm and emergency run stop switch. There is also an emergency phone call box. Elevator has emergency light with dual bulb light. Elevator control box is 28" x 36" and is located in the elevator equipment room. There is also a Montgomery dependable elevator hydraulic pump that is located in the elevator mechanical room. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Add protecting covering for the hot water and drain pipes under the accessible lavatory/sink in the men's and women's rest rooms as per ADAABAG Section 606.5; 22"x20" Porcelain, Lavatory, Wall Hung, Wall Mounted, Located in the men’s restroom 112 inside the ADA stall, on the plumbing wall. Located in the women’s restroom inside the ADA stall. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Change flush control on the ADA water closet in the women's restroom to be on the open side of the water closet as per; ADAABAG Section 604.6; Porcelain, Water Closet, Tankless, Floor Mounted, Automatic flush control. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Add protecting covering for the hot water and drain pipes under the accessible lavatory/sink in the men's and women's rest rooms as per ADAABAG Section 606.5; 20"x20" Porcelain, Lavatory, Wall Hung, Wall Mounted, Located in men's and women's restrooms off the EDR. | 2025
65760 | ZILO B224 Main Zion Lodge | LMAC | Adjust the water flow so that it us at least 4" high, as per ADAABAG Section 602.6, Stainless Steel, Drinking Fountain, Single Basin, Located in the main lobby next to the men’s and women’s restrooms. | 2025
65760 | ZILO B224 Main Zion Lodge | LMCO | Add Emergency Exit Signs on the first floor at the end of the west end of the hallway to be visible when exiting the elevator, in the accounting storage, and (2) in the basement storage rooms to enhance safety when exiting. | 2025
65760 | ZILO B224 Main Zion Lodge | LMLS | Repair guardrail by adding additional sections at the base and adjust balustrades that the gap between them is no greater than 4"; Wood, Guardrail, Painted, 3x6 upper rail, triple 1x6 bottom rail, 1x1 slats with 4” or greater gaps. 6” from deck, 90 LF Located about upper porch | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating paint, patch any minor damage then replace with primer and finish coat. 36"x80" Hollow Core - Metal, Standard Interior Door, Lever Lockset, Painted, One without door, hollow metal frame, with kick plate Located at offices in kitchen, bathrooms and storage at EDR | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating paint, patch minor damage then replace with primer and finish coat. 36"x84" Hollow Core - Metal, Specialty Door, Self Closer, Painted, Metal frame with 10x10 windows with 2” metal trim Located at kitchens between restaurant | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating finish, sand door surface lightly, patch minor damage then replace with new finish coat. 5'x7' Wood, Cased Opening, Stained, Located at internet cubicle | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating paint, caulk all cracks and joints, patch and repair minor damage, then replace with primer and finish coat. Wood, Exterior Stair Construction Assembly, Half-Turn Design, with Steel Pipe Railing, and closed riser, Decking is composite, upper and lower Landing with three treads in-between; one tread either side of Lower landing. Upper landing is 52”x44”. Lower landing is 44”x54”. Upper 3 treads bordered by 4x12 stringers. Treads 44”x11” with 6.5” rises. Upper landing supported by pair of 6x6 posts. Lower steps 11”x39” and 11”x44” respectively. Painted. Located at EDR entry | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. 70" X 328", Carpet, Interior Stair Covering & Finish, 27 linear feet of carpet by 70 inches wide, Located on the stairway leading from the lobby to the upper floor dining room | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. 4", Rubber, Baseboard Trim, 58LF, Located in office near EDR | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Rubber, Baseboard Trim, 48LF Located in coffee bar | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Rubber, Baseboard Trim, 7LF Located in elevator mechanical closet | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in office by the EDR | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located near hostess stand in restaurant | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in offices behind front desk | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in coffee bar | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in office A and B | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in accounting storage | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in elevator mechanical closet | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating paint, caulk all cracks and joints patch minor damage then replace with primer and finish coat. Wood Lap Siding, Exterior Siding Material, where stone is absent on walls, shiplap, Located around entire structure | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating finish, sand siding material lightly, patch any damage, then replace with new finish coat. 1"x12" Wood, Exterior Wall Trim, Painted, 154 LF Located at building corners | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating paint, patch any minor damage then replace with primer and finish coat. 32" X 80", Wood, Exterior Entrance Door, Lockset with Key, Painted, Located at fire riser shed | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating finish, sand door surface lightly, patch minor damage then replace with new finish coat. 36" X 80", Solid Core - Wood, Standard Interior Door, Metal frame With 22”x26” window with 2” metal trim, Located off hallway entry into EDR | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Remove any loose or deteriorating finish, sand door surface lightly, patch minor damage then replace with new finish coat. 29"x29" Wood, Specialty Door, Stained, Blocked pass through opening, with metal frame Located in restaurant bar | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. 40" X 9.5" X 12", Carpet, Interior Stair Covering & Finish, Located in AV room | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Located in AV room | 2025
65760 | ZILO B224 Main Zion Lodge | RMDM | Paint steel support posts. Steel, Structural Support Post, Double 4”x9” posts with 9” gap between with bracket to support wood trellis beams, 127” high, Located in patio area supporting trellis | 2025
65761 | ZILO E512-E513 Deluxe Duplex "Western" Cabin HS-211 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, ,located in Bathroom and vanity/Closet area of each cabin. | 2025
65761 | ZILO E512-E513 Deluxe Duplex "Western" Cabin HS-211 | LMCO | Replace standard outlets in water heater enclosure with GFCI outlets | 2025
65761 | ZILO E512-E513 Deluxe Duplex "Western" Cabin HS-211 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, Painted, Wood, with felt underlayment and metal valleys and 4” step flashing around the chimney, painted., Located top of the cabin. | 2025
65762 | ZILO A500-A503 Deluxe Quadraplex "Western" Cabin HS-206 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and vanity/Closet of each Cabin | 2025
65762 | ZILO A500-A503 Deluxe Quadraplex "Western" Cabin HS-206 | LMCO | Replace standard outlets in water heater enclosures with GFCI Outlets. | 2025
65762 | ZILO A500-A503 Deluxe Quadraplex "Western" Cabin HS-206 | RMDM | Remove any loose or deteriorating paint, patch any minor damage then replace with primer and finish coat. 36" X 82", Wood, Exterior Entrance Door, Painted, vertical board, wood threshold, hospitality hardware., Located at the entrances of each cabin | 2025
65762 | ZILO A500-A503 Deluxe Quadraplex "Western" Cabin HS-206 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, metal valleys and ridges, and 4 inch step flashing around both chimneys painted., Located over the entire roof. | 2025
65764 | ZILO B208 Dormitory (Overlook) HS-208 | CRDM | Replace at end of useful life. Toggle, Single Pole Switch, Located in the basement storage room. | 2025
65764 | ZILO B208 Dormitory (Overlook) HS-208 | LMLS | Replace non working emergency light located at the east end of the hall way by room 7 1/2 12"x6" Wall Mounted, Emergency Lighting, | 2025
65764 | ZILO B208 Dormitory (Overlook) HS-208 | RMDM | Remove any loose or deteriorating finish, sand trim surface lightly, caulk joints and cracks, patch minor damage, then replace with new finish coat. 3" Wood, Baseboard Trim, Painted, Located in all dorm rooms on the main level of the dorm. (648 LF) | 2025
65765 | ZILO B209 Dormitory (Canyon Vista) HS-209 | CRDM | Replace at end of useful life. 36"x80" Hollow Core - Metal, Specialty Door, Bottom is rotting away. Located at the entrance to the boiler room. | 2025
65765 | ZILO B209 Dormitory (Canyon Vista) HS-209 | LMLS | Install seismic strapping to water heater to prevent damage in a seismic event. Gas Fired, Water Heater - Commercial, Rheem, 100 Gallon, with 10" diameter flue venting, Model G91-200-1 Serial URLPA411302746, Located in the laundry room. | 2025
65766 | ZILO B118 Employee's Dormitory (Cottonwood) | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, One per guest room and wet areas. | 2025
65766 | ZILO B118 Employee's Dormitory (Cottonwood) | DM | Replace Molded And Damaged Drywall accessed at fire riser room in the crawlspace area. | 2025
65766 | ZILO B118 Employee's Dormitory (Cottonwood) | DM | Remove the soil which is against the drywall on the interior and exterior of the crawlspace fire riser room to prevent mold growth. Drywall, Interior Wall Covering Material, Unfinished, Located in mechanical shed (21 LF, 8 Ft. high) and in crawlspace around fire riser room (54 LF, 4 Ft. high) | 2025
65766 | ZILO B118 Employee's Dormitory (Cottonwood) | LMLS | Add seismic/earthquake sensitive gas shut-off valve to the gas line.1" Diameter Galvanized Pipe, Gas Supply System, (140 LF) From the gas supply line to the water heater. Located to building. | 2025
65766 | ZILO B118 Employee's Dormitory (Cottonwood) | RMDM | Remove any loose or deteriorating paint, patch any minor damage then replace with primer and finish coat. Drywall, Interior Wall Covering Material, Painted, 707 LF Located throughout bathrooms and dorm rooms in building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | CRDM | Replace at end of useful life. Wood, Guardrail, Painted, Stair rails. 8”x8” posts at base of stairs with 3”x6” top rail and bottom rail 2”x6” and 1”x6”. Slats are 1”x4” vertical @6” OC between rails. A pipe handrail is mounted to the inside of the railing. Posts are 58” in height, top to bottom of rail assembly is 30”. A 3” air gap exists between the bottom rail and retaining wall. 9 LF total Located at either side of south entry steps | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | DM | Fill Hole in Foundation Wall located at the Southeast corner. It has 6 inch round hole bored from it. This hole presently allows water, animals, and debris into the basement and should be filled to prevent further animal infiltration. | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Replace threshold with one that is a maximum of 1/2" at accessible doors and beveled with a slope no greater than 1:2. As per ADAABAG Section 404.2.5. 36"x80" Metal, Exterior Entrance Door, with Panic Hardware, Lockset with Key, Painted, With 22”x28” vision lites Located at south entrance. | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Replace door handle on the recreation room door with one that has a shape that is easy to grasp with one hand and not require tight grasping, tight pinching or twisting of the wrist to operate, as per ADAABAG Section 309.4. 36" X 80", Solid Core - Wood, Standard Interior Door, Located , rec room, | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Add horizontal grab bar on the wall along side the shower seat, but not behind the shower seat for stabilization and transfer as per ADAABAG Section 608.3.2; stainless Steel, Grab Bar,36", Located in both ADA bathrooms.. | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Lower shelf and closet rod to be between 40" and 48" (Currently 64") as per Department of Justice, ADAABAG; 30" X 80" X 6", Wood, Shelving, Located in ADA bedroom 2 and 1 | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Add handrail to other side of the stairway as only one side has a handrail as per ADAABAG Section 504.6, 505.2; Wood, Interior Stair Construction Assembly, Half-Turn Design, with Wood Railing, with closed riser, 18 risers, 16 treads, 37"x76" central landing, wood skirt double 1x12 on both sides of stair, 2” wood railing, 7" rises, 32"x11" treads Located on both ends of building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Replace handrail that is 2" wide with one that is between 1-1/4" - 1-1/2" as per ADAABAG Section 505.7.1, 505.7.2; Wood, Interior Stair Construction Assembly, Half-Turn Design, with Wood Railing, with closed riser, 18 risers, 16 treads, 37"x76" central landing, wood skirt double 1x12 on both sides of stair, 2” wood railing, 7" rises, 32"x11" treads Located on both ends of building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Extend Handrail to 12" beyond the top riser as per ADAABAG Section 505.10.2; Wood, Interior Stair Construction Assembly, Half-Turn Design, with Wood Railing, with closed riser, 18 risers, 16 treads, 37"x76" central landing, wood skirt double 1x12 on both sides of stair, 2” wood railing, 7" rises, 32"x11" treads Located on both ends of building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Replace handrails that have a gripping surface of approximately 1-3/4" with ones that have a gripping surface of between 1-1/4" to 1-1/2" as per ADAABAG Section 505.7.2, 505.7.1 Concrete, Exterior Stair Construction Assembly, Straight-Run Design, with Steel Pipe Railing, and closed riser, 96”x72” top landing/stoop with 3 treads and 4 rises. 7” rises with 11”x72” treads and 1” toe kicks, Located at west entrance | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Replace water closets with one that the toilet seat is between 17" - 19" above the floor as per Department of Justice, ADAABAG; Porcelain, Water Closet, with Tank, Floor Mounted, with Manual Handle Flush Valve, Located in the bathroom units of the accessible dorms. (Dorm Rooms 1 & 2) | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | LMAC | Extend handrails 12" beyond the ramp as per ADAABAG Section 505.10.1 Entrance Ramp, With painted pipe railing, 48 LF of railing Located at west entrance | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | RMDM | Replace at end of useful life. Carpet, Interior Stair Covering & Finish, Located on stairs at both ends of building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | RMDM | Replace at end of useful life. Rubber, Baseboard Trim, 2224 LF Located in hallways, bedrooms, bathrooms and stairways throughout building | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in mechanical closet first floor next to laundry room | 2025
65769 | ZILO B223 New Dormitory (Box Elder) | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, Located in utility closet | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | CRDM | Replace at end of useful life. 36"x40" Roof Mounted, Evaporative Cooler, Evaporative cooler sits on a metal stand that is connected to the roof. One located on the south side of the building also on metal stand. Also located on the roof on the east side of the building. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | CRDM | Replace at end of useful life. 8"x5" , Thermostat, Located on the north wall of the accounting office. One located on the east wall of the recreation hall. One located in the HR office on the north wall. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | CRDM | Replace at end of useful life. Quad Bulb, Fluorescent Light Fixture, with prismatic cover, LED retrofitted. Five lights do not have protective bars on them. Located in the recreation area of the building. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | CRDM | Replace at end of useful life. 4" Diameter Single Bulb, Interior Light Fixture, with glass cover, Located in the cleaning closet next to the main entry. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | DM | Repair damaged drywall located in many spots throughout the gym area. Drywall, Interior Wall Covering Material, Painted, | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Add Self-Closing hinge to bathroom stall door in women's restrooms on ADA Stall as per ADAABAG Section 604.8.1.2; 36"x58" stall door to the ADA compartment Located in the women’s restroom. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Lower coat hook to be a maximum height of 48" currently it is at 59" as per ADAABAG Section 308.3, 603.4; 36"x58" stall door to the ADA compartment Located in the women’s restroom. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Move grab bar in the men's restroom so that the center line of the grab bar is positioned a minimum of 12" to the center line of the toilet as per ADAABAG Section 604.5.2; Stainless Steel, Grab Bar(1) 42”, Located in men’s bathroom | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Add Self-Closing hinge to bathroom stall door in the men's restrooms on ADA Stall as per ADAABAG Section 604.8.1.2; toilet Partition, 14LF and 58" tall with a 36" x 58" stall door. Located in men’s bathroom | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Add coat hook to be a maximum height of 48" as per ADAABAG Section 308.3, 603.4; toilet Partition, 14LF and 58" tall with a 36" x 58" stall door. Located in men’s bathroom | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Adjust urinal height that is mounted at 24 inches above the floor and should be a maximum of 17 inches per ADAABAG Section 605.2. Move urinal to 17" above the floor. Porcelain, Urinal, Tankless, Wall Mounted, with Manual Handle Flush Valve, Located in the men’s restroom. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Adjust Urinal Height. The flush control is mounted at 51 inches above the floor and should be mounted no higher than 44 inches above the floor. Move or replace urinal so that the flush control is no higher than 44 inches above the floor. Porcelain, Urinal, Tankless, Wall Mounted, with Manual Handle Flush Valve, Located in the men’s restroom. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | LMAC | Replace Water Closet. Flush control in men’s restroom is located on the wall side of the water closet and should be on the open side of the water closet per ADAABAG Section 604.6. Replace water closet so that the flush hand control is located on the open side of the water closet. Porcelain, Water Closet, with Tank, Floor Mounted, with Manual Handle Flush Valve, Located in the men's restroom. | 2025
65770 | ZILO B204 Recreation Hall, Regional Offices | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, With 4”x 36” metal transition strips 24LF, Located throughout building except basketball court and bathrooms | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | DM | Replace broken window pane in the north bay 76"x99" Steel, Glazed Window, Painted, (1' x 1' 6" panes) with 3' x 4' swivel tilt operable opening. Loft portion of windows include 84" x 48" Metal Grate - 4" x 4" protective cover. All window panes the wire mesh inside each window pane. (This component is part of the historic fabric of the building) | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | DM | Repair downspout on the SW side of the building where it is coming apart at the junction and the bottom of the downspout is pointing upwards not allowing the water to drain properly. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Replace threshold with one that is a maximum of 1/2" at accessible doors and beveled with a slope no greater than 1:2. As per ADAABAG Section 404.2.5. 32"x78" Wood, Exterior Entrance Door, Lever Handle, Painted, vertical board, painted, wood threshold and western hinges Located in the north bay on the east side and in the South bay on the west side of the building | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Add door knob to the door that has a shape that is easy to grasp with one hand and not require tight grasping, tight pinching or twisting of the wrist to operate As per ADAABAG Section 309.4; 36"x80" Hollow Core - Wood, Standard Interior Door, Six panels,. stained. Located to the storage room off the south bay. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Add kick plate so there is a 10" smooth surface extending the full width of the bottom of the push side of the door as per ADAABAG Section 404.2.10; 36"x80" Hollow Core - Wood, Standard Interior Door, Six panels. With lever lock set, stained. Located to the HR storage and the storage room off the south bay. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Replace door handle on the bathroom door with one that has a shape that is easy to grasp with one hand and not require tight grasping, tight pinching or twisting of the wrist to operate, as per ADAABAG Section 309.4. 32" X 80", Hollow Core - Wood, Standard Interior Door, Six panel. Lever locks, Stained., Located to the restroom off the south bay. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Add kick plate so there is a 10" smooth surface extending the full width of the bottom of the push side of the door as per ADAABAG Section 404.2.10; 32" X 80", Hollow Core - Wood, Standard Interior Door, Six panel. Lever locks, Stained., Located to the restroom off the south bay. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Add handrail on side of stairs that has no rail as per ADAABAG Section 504.6, 505.2; Metal, Handrail, 15 linear foot 2 inch diameter steel pipe. Five steel handrail support. | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Replace water closet with one that is 17"-19" when measured from the floor to the top of the toilet seat as per ADAABAG Section 604.4, also change flush control so that it is located on the open side of the water closet as per ADAABAG Section 604.6; Porcelain, Water Closet, with Tank, Floor Mounted, with Manual Handle Flush Valve, 1.6 gal., standard flush valve, plastic seat., Located in the restroom | 2025
65774 | BICR B550 Birch Creek Machine Shop HS-086 | LMAC | Add protecting covering for the hot water and drain pipes under the accessible lavatory/sink in the men's and women's rest rooms as per ADAABAG Section 606.5; 20' X 18', Porcelain, Lavatory, Wall Hung, Wall Mounted, located in restroom. | 2025
88616 | Lodge Area Maintained Landscape | CRDM | Replace at end of useful life. Walkway, 5’ wide 4” thick. Located between lodge and grass area at the front of the lodge and under benches in front of lodge. | 2025
88616 | Lodge Area Maintained Landscape | LMAC | Replace current guardrails with guardrails that are between 1-1/4" to 1-1/2" in diameter as per ADAABAG Section 505.7.1, 505.7.2, also extend handrails 12" plus one tread beyond the bottom riser as per ADAABAG Section 505.10.3 60" X 7" X 14", Stairs, Stone steps with (7) risers and (6) treads. On the edges is a stone wall that is 12” thick and 4” high. There is a metal railing on both sides of the stairs. 2” diameter metal pole with 2 metal posts., Located west of cabin k 520, D 517, M 523 | 2025
101362 | ZILO C508-C511 Deluxe Quadraplex "Western" Cabin HS-210 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and vanity/Closet of each Cabin | 2025
101362 | ZILO C508-C511 Deluxe Quadraplex "Western" Cabin HS-210 | LMCO | Replace standard outlet in water heater enclosures with GFCI outlets | 2025
101362 | ZILO C508-C511 Deluxe Quadraplex "Western" Cabin HS-210 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, metal valleys and ridges, and 4 inch step flashing around both chimneys painted. Located over the entire roof. | 2025
101363 | ZILO H514-H515 Deluxe Duplex "Western" Cabin HS-212 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101363 | ZILO H514-H515 Deluxe Duplex "Western" Cabin HS-212 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet, and weatherproof cover. | 2025
101363 | ZILO H514-H515 Deluxe Duplex "Western" Cabin HS-212 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101367 | ZILO D516-D517 Deluxe Duplex "Western" Cabin HS-213 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, ,located in Bathroom and vanity/Closet area of each cabin. | 2025
101367 | ZILO D516-D517 Deluxe Duplex "Western" Cabin HS-213 | LMCO | Replace standard outlets in water heater enclosure with GFCI outlets | 2025
101367 | ZILO D516-D517 Deluxe Duplex "Western" Cabin HS-213 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, Painted, Wood, with felt underlayment and metal valleys and 4” step flashing around the chimney, painted., Located top of the cabin. | 2025
101368 | ZILO G518-G519 Deluxe Duplex "Western" Cabin HS-214 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101368 | ZILO G518-G519 Deluxe Duplex "Western" Cabin HS-214 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101368 | ZILO G518-G519 Deluxe Duplex "Western" Cabin HS-214 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101369 | ZILO K520-K521 Deluxe Duplex "Western" Cabin HS-215 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101369 | ZILO K520-K521 Deluxe Duplex "Western" Cabin HS-215 | DM | Repair loose handrail at cabin 520 Wood, Guardrail, Painted, 4”x3” top and bottom rails with (50)2”x2” balusters @4” O.C.(186” long each side), Located around the front porches cabin 520 | 2025
101369 | ZILO K520-K521 Deluxe Duplex "Western" Cabin HS-215 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101369 | ZILO K520-K521 Deluxe Duplex "Western" Cabin HS-215 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and vanity/Closet of each Cabin | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | DM | Replace missing shingles over cabin 523 on the edge of the roof, Cedar Shingle, Roof Finish, with felt underlayment, Painted, metal valleys and ridges, and 4 inch step flashing around both chimneys painted | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | DM | Repair loose balusters (2) at cabin 522, and repair loose guardrails at cabins 523 & 524 Wood, Guardrail, Painted, 4”x3” top and bottom rail 30’-8” with (45)2”x 2” balusters @ 4” O.C. And 27” tall, And a 6”x6” post that is 36” Tall | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | LMCO | Label properly the electrical panel as per NEC Reference Code a.110.22; 20" X 43", Metal Panel Box, Main Electrical Service Panel, Square D brand, with, 42 Breakers, 225 Amp/3 Wire System, Located on east side of building. | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | LMCO | Replace standard outlet in water heater enclosures with GFCI outlets | 2025
101370 | ZILO M522-M525 Deluxe Quadraplex "Western" Cabin HS-216 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, metal valleys and ridges, and 4 inch step flashing around both chimneys painted. Located over the entire roof. | 2025
101371 | ZILO O526-O529 Deluxe Quadraplex "Western" Cabin HS-217 | LMCO | Replace standard outlets with GFCI outlets located in water heater enclosures. | 2025
101371 | ZILO O526-O529 Deluxe Quadraplex "Western" Cabin HS-217 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, metal valleys and ridges, and 4 inch step flashing around both chimneys painted., Located over the entire roof. | 2025
101372 | ZILO F530-F531 Deluxe Duplex "Western" Cabin HS-218 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101372 | ZILO F530-F531 Deluxe Duplex "Western" Cabin HS-218 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101372 | ZILO F530-F531 Deluxe Duplex "Western" Cabin HS-218 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101373 | ZILO B504-B507 Deluxe Quadraplex "Western" Cabin HS-207 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and vanity/Closet of each Cabin | 2025
101373 | ZILO B504-B507 Deluxe Quadraplex "Western" Cabin HS-207 | DM | Repair loose balusters at Cabin 507 Wood, Guardrail, Painted, 4”x3” top and bottom rail 30’-8” with (45)2”x 2” balusters @ 4” O.C. And 27” tall, And a 6”x6” post that is 36” Tall | 2025
101373 | ZILO B504-B507 Deluxe Quadraplex "Western" Cabin HS-207 | LMCO | Label Electrical Panel properly as per NEC Reference Code A.110.22 20" X 43", Metal Panel Box, Main Electrical Service Panel, Square D brand, with, 42 Breakers, 225 Amp/3 Wire System, Located on east side of building. | 2025
101373 | ZILO B504-B507 Deluxe Quadraplex "Western" Cabin HS-207 | LMCO | Replace standard outlet in water heater enclosures with GFCI outlets | 2025
101374 | ZILO I532-I533 Deluxe Duplex "Western" Cabin HS-219 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101374 | ZILO I532-I533 Deluxe Duplex "Western" Cabin HS-219 | DM | Repair damaged Fascia Board at chimney of cabin 532 where it appears to be caused by termites 3"x6" Wood, Fascia Board, Painted (4 LF) Located on the gable end of cabin 532 | 2025
101374 | ZILO I532-I533 Deluxe Duplex "Western" Cabin HS-219 | LMCO | Label properly electrical panel as per NEC Reference Code a.110.22 21" X 38", Metal Panel Box, Main Electrical Service Panel, Square D brand, with, 30 Breakers, 125 Amp/3 Wire System, Surface mounted, Located on the exterior of the cabins under the bathroom window | 2025
101374 | ZILO I532-I533 Deluxe Duplex "Western" Cabin HS-219 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101374 | ZILO I532-I533 Deluxe Duplex "Western" Cabin HS-219 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101375 | ZILO J534-J535 Deluxe Duplex "Western" Cabin HS-220 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101375 | ZILO J534-J535 Deluxe Duplex "Western" Cabin HS-220 | DM | Repair window in cabin 534 that will not open, and repair broken window pane on the SE window of cabin 535 30"x58" Wood, Glazed Window, Double Hung, Double Pane, Painted, 4 over 2 true divided lite, (total of 6 panes) with wood screen, (Note; this is part of the historic fabric of the building.) located in Bedroom area. | 2025
101375 | ZILO J534-J535 Deluxe Duplex "Western" Cabin HS-220 | DM | Repair damaged fascia board at chimney at cabin 534 it appears it was caused by termites; 3"x6" Wood, Fascia Board, Painted (4 LF) Located on the gable ends of cabin 534 | 2025
101375 | ZILO J534-J535 Deluxe Duplex "Western" Cabin HS-220 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101375 | ZILO J534-J535 Deluxe Duplex "Western" Cabin HS-220 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101379 | ZILO L536-L537 Deluxe Duplex "Western" Cabin HS-221 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101379 | ZILO L536-L537 Deluxe Duplex "Western" Cabin HS-221 | DM | Trim bush away from building to prevent unwanted wear and from electrical panel to provide working clearance, located on the west side of the building. | 2025
101379 | ZILO L536-L537 Deluxe Duplex "Western" Cabin HS-221 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101379 | ZILO L536-L537 Deluxe Duplex "Western" Cabin HS-221 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101381 | ZILO N538-N539 Deluxe Duplex "Western" Cabin HS-222 | CRDM | Replace at end of useful life. Push Reset, GFCI Protected Receptacle, located in Bathroom and closet/ vanity area of each cabin | 2025
101381 | ZILO N538-N539 Deluxe Duplex "Western" Cabin HS-222 | DM | Replace missing shingles on the east slope of the roof Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101381 | ZILO N538-N539 Deluxe Duplex "Western" Cabin HS-222 | DM | Repair loose balusters (2) that are in front of cabin 539 Wood, Guardrail, Painted, 4”x3” top and bottom rails with (50)2”x2” balusters @4” O.C.(186” long each side), Located around the front porch. | 2025
101381 | ZILO N538-N539 Deluxe Duplex "Western" Cabin HS-222 | LMCO | Replace standard outlet in water heater enclosure with GFCI outlet | 2025
101381 | ZILO N538-N539 Deluxe Duplex "Western" Cabin HS-222 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, with felt underlayment, Painted, With metal valley flashing And 4” step flashing around both chimneys., Located over entire structure | 2025
101387 | ZILO B552 Maintenance Shed (former Mattress Shed) HS-0087 | CRDM | Replace at end of useful life. 38' X 29' X 11', Wall Heater, Electric Wall Heater, Colman Electric Heater/Cooler Unit located in work room near entry door. | 2025
101387 | ZILO B552 Maintenance Shed (former Mattress Shed) HS-0087 | RMDM | Replace at end of useful life. Vinyl, Interior Floor Covering Material, sheet, - located in work area | 2025
101387 | ZILO B552 Maintenance Shed (former Mattress Shed) HS-0087 | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, and cedar shingle ridges, painted. Covering entire roofing area. | 2025
101387 | ZILO B552 Maintenance Shed (former Mattress Shed) HS-0087 | RMDM | Replace at end of useful life. Carpet, Interior Floor Covering Material, Carpeted, located in office. | 2025
239376 | ZILO Propane Tank Area ( N.W.of Box Elder) | RMDM | Remove any loose or deteriorating paint, repair minor damage, then replace with new finish coat 1' X 6', Wood Slats, Fencing, with 4"x4" wood posts, Stained, 6 Ft. fence screening all sides of the propane farm. 7 Posts. Includes 5 Ft. swinging gate. Gate is framed with 2 x 4 supports. Two 2 x 4 cross members. | 2025
239380 | ZILO Vending Building | RMDM | Remove any loose or deteriorating finish, sand surface lightly, patch minor damage then replace with new finish coat. 6"x6" Structural Wood Columns, Exterior Wall Frame Assembly, (4) corner posts. 8 feet tall. Painted | 2025
239380 | ZILO Vending Building | RMDM | Remove any loose or deteriorating finish, sand surface lightly, patch minor damage then replace with new finish coat. 4" X 4", Exterior Wall Frame Assembly, (5) posts. 8 feet tall. Around the building. | 2025
239380 | ZILO Vending Building | RMDM | Remove any loose or deteriorating paint, caulk all cracks and joints patch minor damage then replace with primer and finish coat. 6" Wood, Exterior Siding Material, Painted, tongue and groove siding inside the posts. 8 foot tall. 20 linear feet. Around three sides of the bending machine building. | 2025
239383 | ZILO Transformer Shed (N.E. Side of Cabin 530-31) | RMDM | Remove any loose or deteriorating paint, patch or repair minor damage, then replace with primer and finish coat. Cedar Shingle, Roof Finish, Painted, With tar paper. Fire retardant. | 2025
239387 | Birch Creek Warehouse Maintained Landscape | RMDM | Repaint concrete trash enclosure wall. 6" Retaining Wall, (21 LF) Located near the south end of the warehouse. | 2025